## README
ORACLE FUSION CLOUD — IMPLEMENTATION ESTIMATOR
README — How to Use This Estimator
1. PURPOSE & SCOPE
This workbook is a benchmark-calibrated effort estimation tool for Oracle Fusion Cloud implementations. It covers the full suite — HCM, ERP Financials, Procurement, SCM, CX, EPM, Integration, Data Migration, Reporting, Security, Testing, OCM, and Programme Management — across all SDLC phases from Inception through Post Go-Live Support. It is designed for use by Delivery Leads, Solution Architects, and Estimation CoE practitioners to produce a defensible, assumption-documented effort estimate at proposal, planning, or re-baselining stages. All unit effort values are grounded in published industry benchmarks (Everest Group, Forrester TEI, Gartner, SFIA v8) and are clearly sourced in the Benchmark Library tab.
2. WORKBOOK STRUCTURE — TAB GUIDE
Tab Name | Purpose | Input / Output
README | This guide. Start here. | Reference
Cover | Project metadata — client name, modules, deployment model, version. | Input
Assumptions | Master control panel. All global levers: project parameters, rate card, complexity multipliers, SDLC phase splits. Change inputs here first. | Input
Module Estimator | Core estimation matrix. 68 components across 12 Oracle Fusion pillars. Each row has: component, complexity, volume driver, unit effort, benchmark source, phase split %, complexity multiplier, base effort, and adjusted effort. | Input + Calc
Benchmark Library | Read-only reference. Unit rates and productivity benchmarks from Everest Group (2023), Forrester TEI (2022–24), Gartner (2022), and SFIA v8. Low / Typical / High ranges per component type. | Reference
Effort Summary | Auto-rolled-up effort by module and by SDLC phase. Pulls from Module Estimator and Assumptions. Includes contingency. | Output
FTE & Role Plan | Role definitions, responsibilities, blended rates, and an 18-month FTE loading grid (month-by-month headcount per role). | Output
Assumptions & Risks | 18 standard estimation assumptions, 11 exclusions, and a 14-row risk register with probability, impact, effort adder %, and mitigations. | Reference + Output
Cost Model | Effort × blended rates → total engagement cost by role band. Includes contingency, management reserve, and phased cost split by SDLC phase. | Output
3. HOW TO USE THIS ESTIMATOR — STEP BY STEP
Step 1 | Fill in the Cover tab
Enter the client name, Oracle modules in scope, deployment model, industry, and date. This is metadata only — it does not affect calculations.
Step 2 | Set global parameters in Assumptions → Section A
Enter: project duration, number of modules, legal entities/countries, integration count (simple vs complex), data migration object count, report count, CEMLI extensions count, contingency %, working days per month, and onshore/offshore split. These drive the cost model and effort summary.
Step 3 | Set your Rate Card in Assumptions → Section B
Review and adjust onshore and offshore daily rates per role band. Blended rates are auto-calculated based on the onshore/offshore split you entered in Step 2.
Step 4 | Adjust complexity in Assumptions → Section C (optional)
The four complexity multipliers (Low=0.7×, Medium=1.0×, High=1.4×, Very High=1.9×) are pre-set to industry norms. Adjust only if your organisation has calibrated data that differs from benchmarks.
Step 5 | Set Volume Drivers and Complexity in Module Estimator — the most important step
For each component row in the Module Estimator tab: • COMPLEXITY (column D): set to L / M / H / VH based on your assessment of this specific component for this client. Drives the multiplier in column M. • VOLUME DRIVER (column E): enter the count of how many of this object you are building. See Section 4 below for a full explanation of what volume means per component type. This is the most sensitive input — small changes here create the largest swings in total effort.
Step 6 | Read outputs — do not edit green cells
Base Effort (col N) = Volume × Unit Effort. Adjusted Effort (col O) = Base Effort × Complexity Multiplier. Totals with contingency are in the bottom two rows of the Module Estimator tab. The Effort Summary, FTE Plan, and Cost Model tabs auto-update from these.
Step 7 | Review and tailor Assumptions & Risks
Check all 18 standard assumptions still hold for your engagement. Strike out any that do not apply. Add engagement-specific assumptions. Review the 14 risk rows — adjust probability/impact and add risks specific to this client's context.
Step 8 | Present the Cost Model
The Cost Model tab shows total engagement cost by role band (base + contingency), plus an indicative cost split by SDLC phase. Use this as the basis for your commercial proposal or internal budget submission.
4. UNDERSTANDING THE VOLUME DRIVER COLUMN (Module Estimator, Column E)
The Volume Driver column answers one question: how many of this thing are we building or configuring? It is separate from complexity. Complexity adjusts the effort rate; volume adjusts how many times you apply that rate. The formula is simply: Base Effort (Days) = Volume Driver × Unit Effort per item Components fall into two distinct categories, and misunderstanding this distinction is the most common source of estimation error.
CATEGORY A — Configuration Components (Volume = 1 in almost all cases)
These are modules or functional areas you configure once as a whole. The unit effort already prices the full end-to-end configuration effort for a standard deployment of that component. Volume = 1 means 'we are configuring this module once for this client.' Increasing volume above 1 is only appropriate when you are genuinely deploying the same component multiple times — for example, configuring Payroll separately for 3 countries with distinct legislative rules (Volume = 3) or setting up separate AR configurations for 4 legal entities with different billing rules (Volume = 4).
Component | Typical Volume | Rationale
General Ledger & Chart of Accounts | 1 | One CoA design per deployment, regardless of account count
Absence Management | 1 | One Absence module configuration, even if many absence types
Payroll Run & Reconciliation | 1 | One payroll process design; use 3 if 3 countries with separate payrolls
Accounts Payable | 1 | One AP configuration; increase only for truly separate AP instances
Supply Chain Planning | 1 | One SCP configuration — forecasting models are a configuration choice, not volume
Security: Role Design & RBAC Model | 1 | One role model per deployment, regardless of number of roles
CATEGORY B — Countable / Repeating Objects (Volume = actual count of objects to build)
These are deliverables where you repeat a defined unit of work N times. Each interface, each migration template, each report, each CEMLI extension is a distinct build. The unit effort is the effort per object; total effort scales linearly with count. This is where the estimate is most sensitive. Moving integrations from 17 to 30, or migration objects from 15 to 40, creates the largest swings in total project effort. These counts should be confirmed through dedicated discovery workshops as early as possible and locked into the scope baseline before the estimate is signed off.
Component | Typical Volume | What to Count | How to Confirm Volume
REST/SOAP Simple Integrations | 17 (example) | Count of distinct interface objects to build. Each = separate OIC flow, test, docs. | Integration inventory workshop, Week 1–2
Complex Real-Time Integrations | 8 (example) | Bidirectional/event-driven interfaces counted separately from batch. | Integration inventory workshop, Week 1–2
FBDI/HDL Migration Templates | 15 (example) | One template per migration object: Employees, Cost Centres, Suppliers, GL Balances, etc. | Data migration object catalogue, Phase 0
OTBI Standard Reports | 20 (example) | Each report is a distinct deliverable: build, test, UAT sign-off. | Reporting catalogue, agreed in Design phase
Custom BIP/OTBI Complex Reports | 10 (example) | Complex reports with joins, calculations, bursting — higher unit effort than standard. | Reporting catalogue, agreed in Design phase
CEMLI Custom Extensions | 10 (example) | Each custom extension (Form Personalisation, BI Publisher, CEMLI) counted separately. | CEMLI register, Design phase; minimise to <15% of OOB scope
Data Migration: Trial Loads | 1 | Volume = 1 (the activity) but unit effort covers all objects in scope for that trial round. | Scoped against migration object catalogue
OAC Dashboards | 8 (example) | Each dashboard canvas counted as a deliverable. | Analytics requirements workshop
WHY VOLUME IS THE MOST SENSITIVE INPUT IN THE ENTIRE ESTIMATOR
A single change in volume on a countable component can move total effort by hundreds of days. Examples at default unit efforts: • Integrations: 17 simple → 30 simple = +78 days of effort • Migration objects: 15 → 40 = +100 days (FBDI templates alone) • Reports: 20 standard + 10 complex → 40 standard + 20 complex = +80 days These three categories alone can swing a project by 250+ days — the equivalent of adding 1–2 FTEs for 6 months. This is why integration discovery, data migration cataloguing, and reporting requirements sign-off must happen before an estimate is committed, and why all three carry dedicated risk rows in the Assumptions & Risks tab.
5. COLOUR CODING CONVENTION
Amber fill / text | INPUT CELL — edit this
Green fill / text | OUTPUT / CALCULATED — do not edit
Blue fill / text | FORMULA or cross-sheet reference
Grey fill | Alternating row background — no meaning
Purple fill / text | RISK or exclusion item
Light red fill | High-complexity or high-risk indicator
Yellow fill | KEY ASSUMPTION — flag for review before committing
6. BENCHMARK SOURCES & PROVENANCE
Everest Group | Oracle Cloud HCM & ERP Adoption Report 2023
Component-level unit effort ranges for HCM, Financials, Integration, and Data Migration. Based on 200+ Oracle Cloud implementations across mid-market and enterprise segments.
Forrester Research (TEI) | Total Economic Impact of Oracle Fusion Cloud (2022–2024 Composite)
Effort percentage splits by work stream (integration, data migration, testing, OCM), full-pillar effort ranges for ERP/HCM/EPM, and programme management overhead benchmarks.
Gartner | ERP Cloud Deployment Benchmarks — Magic Quadrant Companion 2022
Timeline benchmarks, integration counts, CEMLI frequency, test cycle norms, cutover window guidance, and 3-year TCO uplift vs on-premise.
SFIA v8 | Skills Framework for the Information Age — Version 8
Technical productivity benchmarks: developer rates per extension, OIC integration flow build effort, test case development and execution rates, training material ratios.
PMI PMBOK / Prosci ACMP | Project Management Body of Knowledge + Association of Change Management Professionals
Programme management overhead %, OCM activity sizing, and change management effort benchmarks used in PM and OCM rows.
7. GOVERNANCE, LIMITATIONS & CHANGE CONTROL
Estimate validity
This estimate is valid for 12 months from the date on the Cover tab, assuming no change to scope, team composition, or delivery model. Rate card review is recommended at 6 months.
Change control triggers
Any of the following require re-estimation and a formal change request: addition of Oracle modules or countries not in the original scope; integration count exceeding the Assumptions tab by >10%; data migration objects increasing by >20%; CEMLI extensions exceeding the agreed cap; changes to go-live date that compress phases.
What this estimate does not cover
Oracle SaaS subscription/licensing costs; client internal resource time; third-party tool licences; post-hypercare managed services; and all items listed in the Exclusions section of the Assumptions & Risks tab.
Calibration recommendation
After project completion, capture actual effort by component and compare to estimates. Update the unit effort values in the Module Estimator (column F) and the Benchmark Library with your own historical data. Over time, your internal benchmarks will supersede the published sources and the estimator will become self-calibrating.
Escalation
If a volume driver or complexity rating is disputed by the client or delivery team, the Benchmark Library tab provides the source range (Low/Typical/High) that justifies the unit effort used. Always cite the source column (column G of the Module Estimator) when defending an estimate.
Oracle Fusion Cloud Implementation Estimator ¦ Benchmark sources: Everest Group, Forrester TEI, Gartner, SFIA v8 ¦ For internal estimation use only
8. CHANGELOG
v3.2 (this version) | Fixed Effort Summary tab: Section A (Effort by Module) previously used hardcoded Base Effort values and a flat x1.15 'Complexity Adj.' formula disconnected from Module Estimator. Both now SUMIF live from Module Estimator's per-component Base Effort (col N) and Adjusted Effort (col O), grouped by Module/Pillar. Also fixed two mis-referenced Assumptions cells: Contingency % was pulling Assumptions!C13 ('No. of Integrations - Simple') instead of C14 ('Contingency %'); Working Hours/Day (used for the Days-to-Hours conversion in Section B) was pulling Assumptions!C12 ('No. of Integrations - Complex') instead of C16 ('Working Hours per Day'). Totals now reconcile exactly with Module Estimator's own TOTAL WITH CONTINGENCY row. Also fixed Assumptions tab Section B: the Blended Rate formula for all 12 roles was reading C17/C18 (Working Days per Month / Onshore %) instead of C18/C19 (Onshore % / Offshore %), causing it to disagree with the correctly-computed Blended Rate on the Cost Model and FTE & Role Plan tabs for the same roles (e.g. Programme Director showed 710 here vs 1290 there). Both now agree.
v3.1 (prior version) | Original release. Effort Summary tab shipped with the disconnect described above — do not use v3.1 Effort Summary totals for a live estimate.

## Cover
ORACLE FUSION CLOUD — IMPLEMENTATION ESTIMATOR
Enterprise-Grade Effort, FTE & Cost Estimation Framework ¦ Benchmark-Calibrated
Client / Engagement Name | <<Enter Name>>
Oracle Modules in Scope | <<e.g. HCM, ERP, SCM>>
Deployment Model | v3.2
Industry Vertical | <<e.g. Manufacturing, BFSI>>
Estimator Version | v1.0
Prepared By | <<Name>>
Date | <<DD-MMM-YYYY>>
Estimation Basis | Benchmark-calibrated (Forrester TEI, Everest Group, Gartner)
WORKBOOK NAVIGATION GUIDE
1. Assumptions | Global levers – team size, contingency %, blended rates, SDLC coverage
2. Module Estimator | Component-level effort matrix: all Fusion modules × complexity × phase
3. Benchmark Library | Forrester / Everest / Gartner / SFIA unit rates & productivity benchmarks
4. Effort Summary | Consolidated effort by module, phase, role — auto-rolled up from Module sheet
5. FTE & Role Plan | FTE loading plan per role per month across project timeline
6. Assumptions & Risks | Standard estimation assumptions, exclusions, and risk register
7. Cost Model | Effort × blended rates → cost by role band and total engagement cost
INPUT CELLS: Amber fill ¦ FORMULA CELLS: Blue text ¦ OUTPUT CELLS: Green fill

## Assumptions
GLOBAL ASSUMPTIONS & LEVERS — Oracle Fusion Implementation Estimator
A. PROJECT PARAMETERS
Parameter | Value | Unit | Min | Max | Source / Note
Project Duration (months) | 18 | months | 12 | 36 | Everest Group Oracle Cloud avg 14-22 mths (mid-market to enterprise)
No. of Oracle Modules in Scope | 5 | count | 1 | 12 | Adjustable — see Module Estimator tab
No. of Legal Entities / Countries | 3 | count | 1 | 50 | Drives data migration & localisation complexity
No. of Integrations (Interfaces) | 25 | count | 5 | 150 | Gartner: avg 30-50 for mid-market ERP
No. of Data Migration Objects | 15 | count | 5 | 120 | Everest: typical 10-40 objects per deployment
No. of Custom Reports / Analytics | 40 | count | 10 | 300 | Forrester TEI: 30-60 standard; 60-150 complex
No. of Custom Extensions (CEMLI) | 10 | count | 0 | 100 | Best practice: minimise to <15% of OOB
No. of Integrations – Complex | 8 | count | 0 | 50 | Bidirectional, real-time, event-driven
No. of Integrations – Simple | 17 | count | 0 | 100 | Batch/file-based, one-way
Contingency % | 15 | % | 10 | 25 | PMI standard: 10-20%; Oracle programmes 15%
Management Reserve % | 5 | % | 3 | 10 | Programme-level buffer over contingency
Working Hours per Day | 8 | hrs | 7 | 9 | Standard billing day
Working Days per Month | 20 | days | 18 | 22 | Standard; adjust for regional calendars
Onshore % | 30 | % | 0 | 100 | Blended onshore/offshore delivery model
Offshore % | 70 | % | 0 | 100 | Should sum to 100% with Onshore %
B. RATE CARD — BLENDED DAILY RATES (USD)
Role / Band | Onshore Rate ($/day) | Offshore Rate ($/day) | Blended Rate ($/day) | Seniority Level | Typical Engagement %
Programme Director / Engagement Lead | 2200 | 900 | 1290 | Partner / Director | 3%
Solution Architect | 1800 | 750 | 1065 | Senior Manager | 5%
Functional Lead (per module) | 1500 | 600 | 870 | Senior Manager | 12%
Technical Lead (Integration/Dev) | 1600 | 650 | 935 | Senior Manager | 8%
Functional Consultant (Senior) | 1200 | 480 | 696 | Manager | 20%
Functional Consultant (Mid) | 900 | 360 | 522 | Senior Associate | 18%
Technical Developer | 950 | 380 | 551 | Senior Associate | 10%
Data Migration Specialist | 1100 | 440 | 638 | Manager | 7%
Change Management / OCM Lead | 1300 | 520 | 754 | Manager | 5%
Testing Lead / QA Manager | 1000 | 400 | 580 | Manager | 5%
Infrastructure / Cloud Engineer | 1100 | 450 | 645 | Senior Associate | 4%
Project Manager | 1400 | 560 | 812 | Manager | 3%
v3.2 fix: Blended Rate formula corrected -- was reading C17/C18 (Working Days per Month / Onshore %), now reads C18/C19 (Onshore % / Offshore %), matching the Cost Model tab.
C. COMPLEXITY MULTIPLIERS
Complexity Level | Multiplier | Selection Criteria | Config Example | Custom Example | Data Migration Example
Low | 0.7 | • OOB / standard Oracle functionality; minimal configuration beyond defaults • Single legal entity or business unit; no country-specific localisation • Processes closely match Oracle standard; no workarounds or process redesign • Standard approval workflow (1–2 levels); standard RBAC roles sufficient • Source data is clean, well-structured, available in compatible format • Integration is one-way batch/file-based (SFTP/FTP); no transformation logic | › Single-country absence plans & holiday calendars › Standard expense policy with OOB approval › Item category setup with standard attributes | › One-way batch SFTP integration (file-based) › Standard OTBI report using a single subject area › Simple page personalisation (hide/show fields) | › Reference data (departments, grades, jobs) — clean single source › Supplier master from single ERP, no duplicates, standard fields › GL chart of accounts with clear legacy mapping
Medium | 1 | • Some configuration beyond OOB; guided by Oracle best practice • 2–5 legal entities or business units sharing common structures • Minor process deviations handled via Oracle flexfields or lookups • Standard multi-level approval workflow (2–3 levels); standard security model • Source data requires moderate cleansing; mostly 1-to-1 field mapping • Standard REST/SOAP API integration; moderate transformation logic | › Multi-entity GL with intercompany accounting (3 entities) › AP invoice approval with 3-level BPM workflow › Payroll element setup for a single-country payroll | › OIC REST API integration (inbound/outbound, moderate mapping) › OTBI report across 2 subject areas with calculated measures › BPM workflow extension with conditional routing | › Employee master from a single HR system with standard fields › Open AP invoices from a structured ERP with known schema › Item master with 50–70% direct attribute mapping
High | 1.4 | • Significant complexity; multiple exceptions to OOB process • 6–15 legal entities, multi-country, or cross-pillar dependencies • Legislative or regulatory requirements driving non-standard configuration • Complex multi-level approval hierarchies; data security policy design • Source data is poor quality, fragmented across systems, or unstructured • Real-time or bidirectional integration; event-driven or orchestrated flows | › Multi-country payroll with country-specific tax localisations (3+ countries) › WMS warehouse layout with advanced picking, putaway & replenishment rules › Security RBAC design with SoD conflict identification and remediation | › Bidirectional real-time OIC integration with complex transformation logic › Custom payroll Fast Formula with tax override and conditional logic › OAC dashboard with cross-pillar KPIs and multi-source calculated metrics | › Employee data from 3+ HR systems with conflicting schemas › Fixed assets with full depreciation history and NBV reconciliation › BOM/routing from legacy MRP with non-standard structure and UoM
Very High | 1.9 | • Heavily customised or non-standard process; Oracle OOB not fit for purpose • 15+ legal entities, global rollout, or highly regulated (BFSI, Pharma, Defence) • High CEMLI dependency; multiple custom extensions interacting with each other • Real-time multi-system orchestration with complex event handling and retry logic • Legacy data with no clear mapping, large volumes, or critical statutory reconciliation • Concurrent go-live across multiple countries or business units in a single cutover | › Global payroll across 10+ countries with unique legislation per country › Holding company consolidation with complex minority interest & FX elimination › Manufacturing with multi-level BOM, shop floor control, and IoT sensor integration | › ODA chatbot with NLP + multi-system backend orchestration › Multi-system integration hub (ERP + HCM + CRM + 3PL + Banking) › Custom statutory report replacing a government submission format | › Legacy COBOL mainframe data with reverse-engineered schema › Multi-country payroll balances with local statutory year-end carryforward › Inventory from 5+ legacy WMS systems with conflicting UoM, codes and structures
D. SDLC PHASE EFFORT DISTRIBUTION (% of Total Effort)
SDLC Phase | % Effort | Oracle AIM/OUM Ref | Key Activities
Inception / Mobilisation | 5% | Phase 0 | Kick-off, infra setup, team onboarding, governance
Discover & Assess (CRP1) | 12% | OUM: Inception | Current state, gap analysis, Conference Room Pilot 1
Design (CRP2/Blueprint) | 18% | OUM: Elaboration | Future state design, CRP2, solution architecture
Build / Configure | 28% | OUM: Construction | Configuration, development, integration build
Integration & Testing | 17% | OUM: Transition | SIT, UAT, performance test, defect resolution
Data Migration | 8% | OUM: Transition | Data extraction, cleansing, load & reconciliation
Training & OCM | 6% | OUM: Transition | End-user training, change readiness, communications
Go-Live & Cutover | 3% | OUM: Production | Cutover planning, go-live execution, hypercare
Post Go-Live Support | 3% | OUM: Production | Hypercare, stabilisation, knowledge transfer

## Module Estimator
MODULE-LEVEL EFFORT ESTIMATION MATRIX — Oracle Fusion Cloud Implementation
Enter volumetric drivers (yellow cells). Complexity auto-applies benchmark unit effort from Benchmark Library.
Module / Pillar | Component / Sub-Process | Complexity (L/M/H/VH) | Volume Driver (Count) | Unit Effort (Days) — OOB | Benchmark Source | Phase: Discover (%) | Phase: Design (%) | Phase: Build (%) | Phase: Test (%) | Phase: Deploy (%) | Complexity Multiplier | Base Effort (Days) | Adjusted Effort (Days) | Primary Role
▼ COMPLEXITY GUIDE — How to select L / M / H / VH for each row (Column D)
Select the code that best describes the majority of the work in this row. When in doubt between two levels, always choose the higher one and document your rationale. Multipliers are applied automatically from the Assumptions tab.
Level (Code) |  |  | Selection Criteria | [10 empty] | Typical Example for this Sheet
Low (L) ×HL:0.7× |  |  | • OOB / standard Oracle functionality; minimal configuration beyond defaults • Single legal entity or business unit; no country-specific localisation • Processes closely match Oracle standard; no workarounds or process redesign • Standard approval workflow (1–2 levels); standard RBAC roles sufficient • Source data is clean, well-structured, available in compatible format • Integration is one-way batch/file-based (SFTP/FTP); no transformation logic | [10 empty] | › Single-country absence plans & holiday calendars › Standard expense policy with OOB approval › Item category setup with standard attributes
Medium (M) ×HL:1.0× |  |  | • Some configuration beyond OOB; guided by Oracle best practice • 2–5 legal entities or business units sharing common structures • Minor process deviations handled via Oracle flexfields or lookups • Standard multi-level approval workflow (2–3 levels); standard security model • Source data requires moderate cleansing; mostly 1-to-1 field mapping • Standard REST/SOAP API integration; moderate transformation logic | [10 empty] | › Multi-entity GL with intercompany accounting (3 entities) › AP invoice approval with 3-level BPM workflow › Payroll element setup for a single-country payroll
High (H) ×HL:1.4× |  |  | • Significant complexity; multiple exceptions to OOB process • 6–15 legal entities, multi-country, or cross-pillar dependencies • Legislative or regulatory requirements driving non-standard configuration • Complex multi-level approval hierarchies; data security policy design • Source data is poor quality, fragmented across systems, or unstructured • Real-time or bidirectional integration; event-driven or orchestrated flows | [10 empty] | › Multi-country payroll with country-specific tax localisations (3+ countries) › WMS warehouse layout with advanced picking, putaway & replenishment rules › Security RBAC design with SoD conflict identification and remediation
Very High (VH) ×HL:1.9× |  |  | • Heavily customised or non-standard process; Oracle OOB not fit for purpose • 15+ legal entities, global rollout, or highly regulated (BFSI, Pharma, Defence) • High CEMLI dependency; multiple custom extensions interacting with each other • Real-time multi-system orchestration with complex event handling and retry logic • Legacy data with no clear mapping, large volumes, or critical statutory reconciliation • Concurrent go-live across multiple countries or business units in a single cutover | [10 empty] | › Global payroll across 10+ countries with unique legislation per country › Holding company consolidation with complex minority interest & FX elimination › Manufacturing with multi-level BOM, shop floor control, and IoT sensor integration
HCM – Core HR | Enterprise Structures & Legal Entities | M | 3 | 12 | Everest 2023 | 15% | 20% | 45% | 15% | 5% | 1 | 36 | 36 | Functional Consultant
HCM – Core HR | Workforce Structures (Dept/Grade/Position) | M | 1 | 8 | Everest 2023 | 15% | 20% | 45% | 15% | 5% | 1 | 8 | 8 | Functional Consultant
HCM – Core HR | Employee Lifecycle Management | M | 1 | 10 | Gartner 2022 | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Lead
HCM – Core HR | Absence Management | M | 1 | 8 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 8 | 8 | Functional Consultant
HCM – Core HR | Document Management & Person Info | L | 1 | 5 | Everest 2023 | 10% | 15% | 55% | 15% | 5% | 0.7 | 5 | 3.5 | Functional Consultant
HCM – Payroll | Payroll Element Setup & Fast Formulas | H | 1 | 20 | Everest 2023 | 10% | 20% | 45% | 20% | 5% | 1.4 | 20 | 28 | Functional Lead
HCM – Payroll | Payroll Run & Reconciliation | H | 1 | 18 | Forrester TEI | 10% | 15% | 45% | 25% | 5% | 1.4 | 18 | 25.2 | Functional Lead
HCM – Payroll | Tax Localisation & Costing | H | 3 | 15 | Gartner 2022 | 10% | 20% | 40% | 25% | 5% | 1.4 | 45 | 63 | Technical Developer
HCM – Talent | Recruitment & Candidate Management | M | 1 | 10 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
HCM – Talent | Performance Management & Goal Setting | M | 1 | 8 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 8 | 8 | Functional Consultant
HCM – Talent | Learning Management (OLM) | M | 1 | 10 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
HCM – Benefits | Benefit Plans & Eligibility | M | 1 | 12 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Consultant
ERP – Financials | General Ledger & Chart of Accounts | H | 1 | 18 | Forrester TEI | 15% | 20% | 40% | 20% | 5% | 1.4 | 18 | 25.2 | Functional Lead
ERP – Financials | Accounts Payable | M | 1 | 12 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Consultant
ERP – Financials | Accounts Receivable | M | 1 | 12 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Consultant
ERP – Financials | Fixed Assets | M | 1 | 10 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
ERP – Financials | Cash Management & Banking | M | 1 | 8 | Gartner 2022 | 10% | 20% | 50% | 15% | 5% | 1 | 8 | 8 | Functional Consultant
ERP – Financials | Intercompany & Consolidation | H | 3 | 20 | Forrester TEI | 10% | 20% | 45% | 20% | 5% | 1.4 | 60 | 84 | Functional Lead
ERP – Financials | Tax (GTAX / Avalara Integration) | H | 3 | 15 | Forrester TEI | 10% | 20% | 40% | 25% | 5% | 1.4 | 45 | 63 | Technical Lead
ERP – Financials | Expense Management (OIE/iExpense) | L | 1 | 6 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 0.7 | 6 | 4.2 | Functional Consultant
ERP – Procurement | Purchasing & Sourcing | M | 1 | 12 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Consultant
ERP – Procurement | Supplier Portal & Self-Service | M | 1 | 10 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
ERP – Procurement | Contract Management | M | 1 | 8 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 8 | 8 | Functional Consultant
SCM | Inventory Management | M | 1 | 12 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Lead
SCM | Order Management | H | 1 | 18 | Forrester TEI | 10% | 20% | 45% | 20% | 5% | 1.4 | 18 | 25.2 | Functional Lead
SCM | Supply Chain Planning (SCP/S&OP) | H | 1 | 22 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 22 | 30.8 | Functional Lead
SCM | Manufacturing (WIP/BOM/Routing) | H | 1 | 25 | Everest 2023 | 10% | 20% | 45% | 20% | 5% | 1.4 | 25 | 35 | Functional Lead
SCM | Quality Management | M | 1 | 10 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
SCM | Warehouse Management (WMS) | H | 1 | 20 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 20 | 28 | Functional Lead
SCM | Procurement Contracts | L | 1 | 6 | Everest 2023 | 10% | 20% | 55% | 10% | 5% | 0.7 | 6 | 4.2 | Functional Consultant
CX – Sales | Opportunity & Pipeline Management | M | 1 | 10 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
CX – Sales | Configure Price Quote (CPQ) | H | 1 | 20 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 20 | 28 | Functional Lead
CX – Service | Service Requests & Case Management | M | 1 | 10 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Functional Consultant
CX – Marketing | Campaign & Lead Management (Eloqua) | M | 1 | 12 | Forrester TEI | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Consultant
EPM | Planning & Budgeting (EPBCS) | H | 1 | 25 | Forrester TEI | 10% | 20% | 45% | 20% | 5% | 1.4 | 25 | 35 | Functional Lead
EPM | Financial Consolidation (FCCS) | H | 1 | 22 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 22 | 30.8 | Functional Lead
EPM | Account Reconciliation (ARCS) | M | 1 | 12 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 12 | 12 | Functional Consultant
EPM | Profitability & Cost Management (PCM) | H | 1 | 18 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 18 | 25.2 | Functional Lead
Integration | REST/SOAP API Integrations (Simple) | M | 17 | 6 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 102 | 102 | Technical Lead
Integration | Real-Time / Event-Driven Integrations (Complex) | H | 8 | 14 | Forrester TEI | 10% | 20% | 45% | 20% | 5% | 1.4 | 112 | 156.8 | Technical Lead
Integration | OIC Flow Design & Orchestration | M | 1 | 15 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 15 | 15 | Technical Lead
Integration | Legacy ERP / Custom App Integration | H | 5 | 18 | Forrester TEI | 10% | 20% | 40% | 25% | 5% | 1.4 | 90 | 126 | Technical Lead
Data Migration | Data Extraction & Profiling | M | 1 | 12 | Everest 2023 | 20% | 20% | 35% | 20% | 5% | 1 | 12 | 12 | Data Migration Specialist
Data Migration | Data Cleansing & Transformation | H | 1 | 18 | Forrester TEI | 15% | 20% | 40% | 20% | 5% | 1.4 | 18 | 25.2 | Data Migration Specialist
Data Migration | FBDI/HDL Template Build (per object) | M | 15 | 4 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 60 | 60 | Technical Developer
Data Migration | Migration Trial Loads & Reconciliation | H | 1 | 15 | Gartner 2022 | 10% | 10% | 30% | 45% | 5% | 1.4 | 15 | 21 | Data Migration Specialist
Data Migration | Cutover Plan & Execution | H | 1 | 10 | Everest 2023 | 5% | 5% | 15% | 20% | 55% | 1.4 | 10 | 14 | Project Manager
Reporting | OTBI/BIP Standard Reports | L | 20 | 1.5 | Everest 2023 | 5% | 15% | 55% | 20% | 5% | 0.7 | 30 | 21 | Technical Developer
Reporting | Custom BI Reports (complex) | H | 10 | 5 | Forrester TEI | 5% | 15% | 50% | 25% | 5% | 1.4 | 50 | 70 | Technical Developer
Reporting | OTBI Subject Area Extension | H | 5 | 6 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 30 | 42 | Technical Lead
Reporting | Oracle Analytics Cloud (OAC) Dashboards | H | 8 | 8 | Gartner 2022 | 10% | 20% | 45% | 20% | 5% | 1.4 | 64 | 89.6 | Technical Lead
Security | Role Design & RBAC Model | H | 1 | 20 | Gartner 2022 | 10% | 25% | 40% | 20% | 5% | 1.4 | 20 | 28 | Functional Lead
Security | User Provisioning & SSO | M | 1 | 10 | Everest 2023 | 10% | 20% | 50% | 15% | 5% | 1 | 10 | 10 | Technical Lead
Security | SoD Conflict Analysis & Remediation | H | 1 | 15 | Forrester TEI | 15% | 20% | 40% | 20% | 5% | 1.4 | 15 | 21 | Functional Lead
Testing & QA | Test Strategy & Test Plan | M | 1 | 10 | SFIA v8 | 15% | 25% | 30% | 25% | 5% | 1 | 10 | 10 | Testing Lead
Testing & QA | Test Script Development | M | 1 | 20 | SFIA v8 | 5% | 15% | 55% | 20% | 5% | 1 | 20 | 20 | Functional Consultant
Testing & QA | System Integration Testing (SIT) | H | 1 | 25 | Everest 2023 | 5% | 5% | 25% | 60% | 5% | 1.4 | 25 | 35 | Testing Lead
Testing & QA | User Acceptance Testing (UAT) Facilitation | M | 1 | 20 | SFIA v8 | 0% | 5% | 15% | 75% | 5% | 1 | 20 | 20 | Testing Lead
Testing & QA | Performance & Load Testing | H | 1 | 15 | Gartner 2022 | 5% | 5% | 20% | 65% | 5% | 1.4 | 15 | 21 | Technical Lead
OCM & Training | Change Impact Assessment | M | 1 | 10 | Prosci/ACMP | 20% | 30% | 25% | 20% | 5% | 1 | 10 | 10 | Change Management Lead
OCM & Training | Stakeholder Engagement & Comms | M | 1 | 15 | Prosci/ACMP | 15% | 25% | 30% | 25% | 5% | 1 | 15 | 15 | Change Management Lead
OCM & Training | [11 empty] | 0 | 0 | Change Management Lead
OCM & Training | [11 empty] | 0 | 0 | Functional Consultant
OCM & Training | End-User Training Delivery | M | 1 | 15 | Prosci/ACMP | 0% | 5% | 15% | 20% | 60% | 1 | 15 | 15 | Functional Consultant
Programme Mgmt | Project Management (end-to-end) | H | 1 | 30 | PMI PMBOK | 15% | 20% | 30% | 20% | 15% | 1.4 | 30 | 42 | Project Manager
Programme Mgmt | Governance & Steering | M | 1 | 10 | PMI PMBOK | 15% | 20% | 30% | 20% | 15% | 1 | 10 | 10 | Programme Director
Programme Mgmt | Risk & Issue Management | M | 1 | 8 | PMI PMBOK | 15% | 20% | 30% | 20% | 15% | 1 | 8 | 8 | Project Manager
Programme Mgmt | Architecture Governance & Reviews | H | 1 | 12 | Gartner 2022 | 20% | 25% | 30% | 20% | 5% | 1.4 | 12 | 16.8 | Solution Architect
Programme Mgmt | Infrastructure & Cloud Setup (OCI) | H | 1 | 15 | Everest 2023 | 30% | 20% | 30% | 15% | 5% | 1.4 | 15 | 21 | Infrastructure Engineer
TOTAL BASE EFFORT (BEFORE CONTINGENCY) | [11 empty] | 1491 | 1835.7
TOTAL WITH CONTINGENCY (+ 15% from Assumptions C13) | [12 empty] | 2111.055

## Benchmark Library
INDUSTRY BENCHMARK LIBRARY — Oracle Fusion Cloud Implementation Unit Rates
EVEREST GROUP — Oracle Fusion HCM/ERP Cloud (2023 Enterprise Adoption Report)
Benchmark Item | Category | Low | High | Typical | Unit | Context / Notes
HCM Core HR setup (single country) | Module Setup | 10 | 16 | 13 | Man-days | Mid-Market (2,500–10,000 EE)
HCM Payroll (complex fast formulas) | Module Setup | 18 | 28 | 22 | Man-days | Enterprise, multiple pay-groups
Financials GL / CoA Design | Configuration | 14 | 22 | 18 | Man-days | Multi-entity, shared services
AP Full Configuration | Configuration | 10 | 14 | 12 | Man-days | Standard 3-way match
Integration – Simple (FBDI/REST batch) | Integration | 4 | 8 | 6 | Man-days | Per interface object
Integration – Complex (real-time OIC) | Integration | 10 | 18 | 14 | Man-days | Bidirectional, orchestrated
Data Migration – FBDI object (cleanse+load) | Data Migration | 3 | 6 | 4 | Man-days | Per migration object
OTBI Standard Report | Reporting | 1 | 2 | 1.5 | Man-days | OOB subject area
Custom BIP/OTBI Complex Report | Reporting | 4 | 7 | 5 | Man-days | With calculations, joins
End-User Training (hrs/user) | Training | 4 | 8 | 6 | Hours | Role-based; blended delivery
Hypercare Support (per module/month) | Post Go-Live | 5 | 10 | 7 | Man-days | Stabilisation period
FORRESTER TEI — Oracle Cloud ERP/HCM Implementations (2022–2024 Composite)
Benchmark Item | Category | Low | High | Typical | Unit | Context / Notes
Programme Management overhead | PM | 12 | 18 | 15 | % effort | Of total delivery effort
ERP Financials – full pillar | Module | 220 | 380 | 300 | Man-days | GL/AP/AR/FA/CM – enterprise
HCM – full pillar (HR+Pay+Talent) | Module | 180 | 320 | 250 | Man-days | Global, multi-country payroll
SCM – full pillar | Module | 200 | 360 | 280 | Man-days | Mfg+OMS+Planning+WMS
Integration effort (% of total) | Integration | 15 | 25 | 20 | % effort | Typical integration ratio
Data Migration (% of total) | Data Migration | 8 | 15 | 12 | % effort | Of total project effort
Testing (% of total) | Testing | 15 | 22 | 18 | % effort | SIT+UAT+Perf
OCM / Change (% of total) | OCM | 6 | 12 | 8 | % effort | Incl. comms, training
Security & Role Design (enterprise) | Security | 15 | 25 | 20 | Man-days | RBAC design + SoD
EPM Planning (EPBCS) | Module | 140 | 240 | 190 | Man-days | Enterprise planning + budgeting
GARTNER — ERP Cloud Deployment Benchmarks (2022 Magic Quadrant Companion)
Benchmark Item | Category | Low | High | Typical | Unit | Context / Notes
Overall project duration – mid-market | Timeline | 10 | 14 | 12 | Months | 5–8 modules, 1–3 entities
Overall project duration – enterprise | Timeline | 18 | 30 | 22 | Months | Full suite, multi-country
Effort: Vendor PS vs SI split | Resourcing | 20 | 30 | 25 | % SI | Oracle PS typically 20-30%
CEMLI (custom ext.) per project avg | Customisation | 10 | 40 | 20 | Count | Best practice: minimise
Integration count – mid-market | Integration | 20 | 40 | 30 | Count | ERP + HCM + legacy
Integration count – enterprise | Integration | 50 | 150 | 80 | Count | Full enterprise landscape
Test cycles (SIT rounds) | Testing | 2 | 3 | 2.5 | Rounds | Typical SIT iterations
UAT duration | Testing | 3 | 6 | 4 | Weeks | Business-led UAT window
Cutover window | Cutover | 1 | 3 | 2 | Weekends | Hard cutover + parallel run
Hypercare period | Post Go-Live | 4 | 8 | 6 | Weeks | L1/L2 hyper support
Total cost of ownership – 3yr uplift | Finance | 120 | 180 | 150 | % vs on-prem | TCO comparison cloud vs legacy
SFIA v8 / ITSM — Oracle Cloud Technical Benchmarks
Benchmark Item | Category | Low | High | Typical | Unit | Context / Notes
Solution Architect productivity (days/design point) | Architecture | 3 | 6 | 4 | Days | Per significant design decision
Developer productivity (CEMLI, days/extension) | Development | 5 | 12 | 8 | Man-days | Per custom extension object
Report development (hrs/report) | Reporting | 6 | 16 | 10 | Hours | Complex analytics report
OIC integration flow build | Integration | 3 | 8 | 5 | Man-days | Per integration flow
Test case development (hrs/test) | Testing | 0.5 | 2 | 1 | Hours | Per functional test case
Test execution (hrs/test/cycle) | Testing | 0.25 | 1 | 0.5 | Hours | Per test case per cycle
Training material (hrs/hr of content) | Training | 20 | 40 | 30 | Hours | Development to delivery ratio
Knowledge transfer (days/consultant) | KT | 3 | 5 | 4 | Man-days | Per senior resource

## Effort Summary
CONSOLIDATED EFFORT SUMMARY — By Module & SDLC Phase
v3.2 fix: Base Effort, Complexity Adj., and Contingency now roll up live from Module Estimator (previously hardcoded / mis-referenced Assumptions!C12-C13 instead of C14/C16). See README changelog.
A. EFFORT BY MODULE (Days — Adjusted for Complexity + Contingency)
Module / Pillar | Base Effort (Days) | Complexity Adj. (Days) | Contingency (Days) | Total Effort (Days) | % of Total | Est. Duration (weeks) | Avg FTE Required | Key Roles
HCM – Core HR | 67 | 65.5 | 9.825 | 75.325 | 3.568%
HCM – Payroll | 83 | 116.2 | 17.43 | 133.63 | 6.33%
HCM – Talent | 28 | 28 | 4.2 | 32.2 | 1.525%
HCM – Benefits | 12 | 12 | 1.8 | 13.8 | 0.6537%
ERP – Financials | 171 | 218.4 | 32.76 | 251.16 | 11.9%
ERP – Procurement | 30 | 30 | 4.5 | 34.5 | 1.634%
SCM | 113 | 145.2 | 21.78 | 166.98 | 7.91%
CX – Sales | 30 | 38 | 5.7 | 43.7 | 2.07%
CX – Service | 10 | 10 | 1.5 | 11.5 | 0.5448%
CX – Marketing | 12 | 12 | 1.8 | 13.8 | 0.6537%
EPM | 77 | 103 | 15.45 | 118.45 | 5.611%
Integration | 319 | 399.8 | 59.97 | 459.77 | 21.78%
Data Migration | 115 | 132.2 | 19.83 | 152.03 | 7.202%
Reporting | 174 | 222.6 | 33.39 | 255.99 | 12.13%
Security | 45 | 59 | 8.85 | 67.85 | 3.214%
Testing & QA | 90 | 106 | 15.9 | 121.9 | 5.774%
OCM & Training | 40 | 40 | 6 | 46 | 2.179%
Programme Mgmt | 75 | 97.8 | 14.67 | 112.47 | 5.328%
TOTAL | 1491 | 1835.7 | 275.355 | 2111.055 | 100%
B. EFFORT BY SDLC PHASE
SDLC Phase | % Split | Effort (Days) | Effort (Hours) | Elapsed Weeks | Avg FTE
Inception/Mobilise | 5% | 105.5528 | 844.422
Discover & Assess | 12% | 253.3266 | 2026.6128
Design (Blueprint) | 18% | 379.9899 | 3039.9192
Build / Configure | 28% | 591.0954 | 4728.7632
Integration & Testing | 17% | 358.8793 | 2871.0348
Data Migration | 8% | 168.8844 | 1351.0752
Training & OCM | 6% | 126.6633 | 1013.3064
Go-Live / Cutover | 3% | 63.3316 | 506.6532
Post Go-Live Support | 3% | 63.3316 | 506.6532

## FTE & Role Plan
FTE LOADING PLAN & ROLE MAPPING — Oracle Fusion Cloud Implementation
Month columns assume 18-month project (adjust in Assumptions). FTE = Effort Days / (20 working days/month).
A. ROLE DEFINITION & RESPONSIBILITIES
Role | Level | Key Responsibilities | Avg Daily Rate (Blended) | Total Effort (Days) | Peak FTE
Programme Director | Partner | Overall programme governance, exec steering, P&L | 1290 | 30 | 1
Solution Architect | Senior Manager | End-to-end architecture, integration design, governance | 1065 | 80 | 1
HCM Functional Lead | Senior Manager | Lead HCM stream: Core HR, Payroll, Talent, Benefits | 870 | 150 | 1
Finance Functional Lead | Senior Manager | Lead Finance stream: GL, AP, AR, FA, Tax | 870 | 160 | 1
SCM Functional Lead | Senior Manager | Lead SCM: Inventory, OMS, Manufacturing, WMS | 870 | 140 | 1
Technical/Integration Lead | Senior Manager | OIC design, CEMLI builds, API governance | 935 | 120 | 1
Functional Consultant x3 | Manager | Module configuration, CRP facilitation, UAT support | 696 | 350 | 2
Functional Consultant x4 | Senior Associate | Config, testing, training, data migration tasks | 522 | 400 | 3
Technical Developer x2 | Senior Associate | CEMLI, OIC flows, BIP/OTBI reports, security roles | 551 | 200 | 1
Data Migration Specialist | Manager | Extract, cleanse, FBDI build, trial loads, reconciliation | 638 | 100 | 1
Change Management Lead | Manager | OCM strategy, comms, training design, readiness assessment | 754 | 80 | 1
Testing Lead | Manager | Test strategy, SIT/UAT management, defect triage | 580 | 90 | 1
Infrastructure Engineer | Senior Associate | OCI setup, SSO, security patching, performance | 645 | 50 | 1
Project Manager | Manager | Plan, RAID, governance packs, steering reporting | 812 | 90 | 1
B. MONTHLY FTE RAMP PLAN (18-Month Programme)
Role / Phase | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | Peak FTE | Total Days
Programme Director | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 360
Solution Architect | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2 | 360
HCM Functional Lead |  | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [7 empty] | 2 | 280
Finance Functional Lead |  | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [7 empty] | 2 | 280
SCM Functional Lead |  | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [7 empty] | 2 | 280
Technical/Integ. Lead |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | [6 empty] | 2 | 300
Functional Consultants |  | 1 | 2 | 3 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 1 | [6 empty] | 4 | 580
Technical Developers |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | [8 empty] | 2 | 260
Data Migration Specialist |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | [7 empty] | 2 | 240
Change Mgmt Lead |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | 240
Testing Lead |  |  |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 1 | [7 empty] | 2 | 200
Infrastructure Engineer | 1 | 1 | 1 | 1 | [14 empty] | 1 | 80
Project Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 360
TOTAL FTE (per month) | 4 | 9 | 14 | 19 | 21 | 21 | 21 | 18 | 17 | 14 | 12 | 6 | 4 | 3 | 2 | 2 | 2 | 2

## Assumptions & Risks
ESTIMATION ASSUMPTIONS, EXCLUSIONS & RISK REGISTER
A. STANDARD ESTIMATION ASSUMPTIONS
Oracle Fusion Cloud is the confirmed target platform; no on-premise deployment |  |  |  |  | Scope
Effort covers System Integrator (SI) delivery only; Oracle Product Support and Client internal effort are excluded unless stated |  |  |  |  | Scope
All modules listed in the Assumptions tab are in scope; any additions will require re-estimation |  |  |  |  | Scope
Client SMEs will be available ≥40% of their time during Discover, Design, and UAT phases |  |  |  |  | Access
Client will provide timely access to legacy system data, current process documentation, and IT environments |  |  |  |  | Access
Business decisions on process design and configuration choices will be made within 5 business days of presentation |  |  |  |  | Decisions
Source data quality is assumed acceptable; poor data quality requiring extensive cleansing will add effort |  |  |  |  | Data
Number of data migration objects is as stated in Assumptions tab; additions will be change-controlled |  |  |  |  | Data
Integration count and complexity as stated; major undiscovered interfaces will be change-controlled |  |  |  |  | Integrations
Third-party system owners will provide API documentation and sandbox environments within 4 weeks of project start |  |  |  |  | Integrations
Oracle Cloud environments (DEV, TEST, PROD) will be provisioned by the client within 2 weeks of project kick-off |  |  |  |  | Environment
Client business users will actively participate in and lead UAT; SI provides facilitation and defect management only |  |  |  |  | Testing
Training delivery will be conducted in English unless localisation is explicitly in scope |  |  |  |  | Training
A single-phase 'big bang' cutover is assumed; phased/parallel run will require additional effort |  |  |  |  | Cutover
Blended onshore/offshore delivery model as per Assumptions tab; changes to mix will affect blended rate |  |  |  |  | Resourcing
Daily rates are as per the Rate Card in the Assumptions tab; valid for 12 months from proposal date |  |  |  |  | Rates
15% contingency is included for known unknowns; management reserve of 5% is excluded from this estimate |  |  |  |  | Contingency
No major regulatory change during the project period; any new legislative requirements will be change-controlled |  |  |  |  | Regulatory
B. STANDARD EXCLUSIONS FROM THIS ESTIMATE
✗ Oracle licensing costs (SaaS subscription fees)
✗ Client internal resource costs (business SMEs, IT staff time)
✗ Third-party software licences (middleware, testing tools, BI platforms)
✗ Infrastructure / hardware costs for retained on-premise systems
✗ Business process re-engineering (BPR) beyond Oracle standard process adoption
✗ Post-hypercare ongoing AMS/managed services (separate engagement)
✗ Country-specific legal/statutory localisation beyond standard Oracle localisation packs
✗ Legacy system decommissioning and data archival
✗ Organisational restructuring or headcount change management beyond programme OCM
✗ Independent Testing/Assurance (ITA) if procured separately
✗ Oracle Primavera, Agile PLM, or other non-Fusion Cloud products
C. ESTIMATION RISK REGISTER
Risk Description | Category | Probability (H/M/L) | Impact (H/M/L) | Effort Adder (%) | Mitigation
Scope creep from undiscovered business requirements | Scope | H | H | +10% | Fixed-scope SoW with change control; CRP gates
Poor data quality in legacy systems requiring extensive cleanse | Data | H | H | +15% | Data quality assessment in Phase 0; early profiling
Client SME availability below 40% commitment | Resourcing | H | M | +10% | Escalation path to Steering; contractual commitment
Integration complexity higher than estimated (undiscovered APIs) | Integration | M | H | +12% | Integration discovery workshop in Week 2
Configuration decisions delayed beyond 5-day SLA | Governance | M | M | +8% | Decision log; 48hr escalation to Programme Sponsor
Regulatory change during project (tax, payroll legislation) | Regulatory | M | H | +10% | Change control; buffer in payroll and tax streams
Oracle Cloud quarterly update breaking custom configuration | Technical | M | M | +5% | Regression test suite; Oracle release calendar monitoring
Cutover complexity greater than estimated (data volumes/reconciliation) | Cutover | M | H | +12% | Mock cutover rehearsal; 2 dry runs planned
Key SI resources leave mid-project | Resourcing | L | H | +8% | Knowledge capture; redundancy in leads; succession plan
Third-party system owners unresponsive for integration testing | Integration | M | M | +10% | SLA in integration agreement; early engagement
Oracle environment provisioning delays (OCI setup) | Environment | L | M | +5% | Cloud readiness checklist; OCI fast-track provisioning
User adoption risk – resistance to new processes | OCM | M | H | +8% | OCM strategy; change champion network; early UAT involvement
Multi-country payroll localisation more complex than estimated | Regulatory | H | H | +20% | Country-specific discovery session; local tax expert
Report/analytics demand exceeds estimate (scope creep) | Scope | H | M | +10% | Reporting catalogue fixed in Design; CR for additions

## Cost Model
COMMERCIAL COST MODEL — Oracle Fusion Cloud Implementation
A. EFFORT-TO-COST BRIDGE BY ROLE BAND
Role / Band | Effort (Days) | Onshore Rate ($/day) | Offshore Rate ($/day) | Blended Rate ($/day) | Onshore Cost ($) | Offshore Cost ($) | Total Cost ($)
Programme Director | 30 | 2200 | 900 | 1290 | 19800 | 18900 | 38700
Solution Architect | 80 | 1800 | 750 | 1065 | 43200 | 42000 | 85200
HCM Functional Lead | 150 | 1500 | 600 | 870 | 67500 | 63000 | 130500
Finance Functional Lead | 160 | 1500 | 600 | 870 | 72000 | 67200 | 139200
SCM Functional Lead | 140 | 1500 | 600 | 870 | 63000 | 58800 | 121800
Technical / Integ. Lead | 120 | 1600 | 650 | 935 | 57600 | 54600 | 112200
Functional Consultants | 350 | 1200 | 480 | 696 | 126000 | 117600 | 243600
Technical Developers | 200 | 950 | 380 | 551 | 57000 | 53200 | 110200
Data Migration Specialist | 100 | 1100 | 440 | 638 | 33000 | 30800 | 63800
Change Mgmt Lead | 80 | 1300 | 520 | 754 | 31200 | 29120 | 60320
Testing Lead | 90 | 1000 | 400 | 580 | 27000 | 25200 | 52200
Infrastructure Engineer | 50 | 1100 | 450 | 645 | 16500 | 15750 | 32250
Project Manager | 90 | 1400 | 560 | 812 | 37800 | 35280 | 73080
BASE DELIVERY COST (before contingency) | [6 empty] | 1263050
CONTINGENCY (15% — Assumptions C14) | [6 empty] | 189457.5
TOTAL ESTIMATED ENGAGEMENT COST | [6 empty] | 1452507.5
MANAGEMENT RESERVE (5% — advisory only, not included above) | [6 empty] | 72625.375
B. INDICATIVE COST BY SDLC PHASE
SDLC Phase | % Effort | Phase Cost ($) | % of Total
Inception/Mobilise | 5% | 72625.375
Discover & Assess | 12% | 174300.9
Design (Blueprint) | 18% | 261451.35
Build / Configure | 28% | 406702.1
Integration & Testing | 17% | 246926.275
Data Migration | 8% | 116200.6
Training & OCM | 6% | 87150.45
Go-Live / Cutover | 3% | 43575.225
Post Go-Live Support | 3% | 43575.225