POINT OF VIEW — ADDENDUM

How AI Changes the Way We Estimate

Oracle Programs

A methodology-level guide to estimation in the AI era

Covering Greenfield & Brownfield | Implementation · Upgrade · AMS

July 2026

# Why Traditional Estimation No Longer Works

Traditional Oracle program estimation has, for decades, followed one of three approaches:

- 1.  Activity-Based Estimation (ABE) — decompose work into tasks, assign hours per task based on historical benchmarks, sum to a total.

- 2.  Object-Based Estimation (OBE) — count RICE/CEMLI/WRICEF objects, classify by complexity (High / Medium / Low), apply standard hours per type.

- 3.  Analogy-Based Estimation — compare to a previous similar program and scale.

All three methods share a core assumption: effort is proportional to the volume of work a human performs. AI breaks this assumption permanently.

⚠ The Fundamental Shift Traditional methods estimate the INPUT (hours of human effort). AI-era methods must estimate the OUTPUT (deliverables produced per unit of augmented human+AI effort). If a senior developer with AI can produce a RICE object in 18 hours instead of 40, your benchmark table is wrong — not your developer.

## The Three Failure Modes of Traditional Estimates in an AI World

- Failure Mode 1:  Using the same benchmark hours without an AI productivity adjustment — leads to overestimation and loss of competitive bids.

- Failure Mode 2:  Applying blanket AI discounts (e.g. "cut everything by 30%") without understanding which activities AI impacts and which it does not — leads to underestimation and margin erosion.

- Failure Mode 3:  Ignoring the new effort categories AI introduces (AI tool setup, prompt engineering, output validation, AI model governance) — leads to scope gaps.

# The AI-Augmented Estimation Framework

The new framework replaces flat hour-per-task benchmarks with a structured model that accounts for AI participation at the task level. It has five components:

## Component 1 — AI Participation Classification (APC)

Before estimating any work package, classify each SDLC activity into one of four AI Participation Levels:

| APC Level | Definition | AI Role | Human Role | Effort Adjustment |
| --- | --- | --- | --- | --- |
| APC-1 Fully Human | Activities where AI has no meaningful role | None / advisory | Full ownership | 0% reduction — no change |
| APC-2 AI-Assisted | AI accelerates but human leads and reviews all output | Drafts, suggests, generates first cut | Reviews, corrects, approves | 25–40% reduction |
| APC-3 AI-Augmented | AI does the majority of production work; human validates and directs | Produces artifacts, executes tasks | Quality gates, direction, exceptions | 45–65% reduction |
| APC-4 AI-Led | AI operates autonomously on well-defined, repeatable tasks with human oversight only | Executes end-to-end | Monitors, escalates exceptions | 65–80% reduction |

## Component 2 — Activity-Level APC Mapping

Apply APC levels to every SDLC activity, for both Greenfield and Brownfield scenarios:

| SDLC Activity | APC — Greenfield | APC — Brownfield Upgrade |
| --- | --- | --- |
| Executive Workshops / Business Process Design | APC-1 (Fully Human) | APC-1 (Fully Human) |
| Stakeholder Management & Change Mgmt | APC-1 (Fully Human) | APC-1 (Fully Human) |
| Fit-Gap / Solution Architecture | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |
| Configuration Workbook Design | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |
| Configuration Data Entry / Setup | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Custom Code / Extension Development | APC-3 (AI-Augmented) | APC-2 to 3 (varies by complexity) |
| Legacy Code Impact Analysis (Upgrade) | N/A | APC-3 (AI-Augmented) |
| Data Profiling & Source Analysis | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Source-to-Target Data Mapping | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Data Transformation / Cleanse | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Migration Script Development | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Migration Validation / Reconciliation | APC-4 (AI-Led) | APC-4 (AI-Led) |
| Test Case Design (Functional) | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |
| Test Script Development (Automated) | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Regression Test Execution | APC-4 (AI-Led) | APC-4 (AI-Led) |
| UAT Support & Defect Management | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |
| Documentation (FDD/TDD/Config) | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Training Material Development | APC-3 (AI-Augmented) | APC-2 (AI-Assisted) |
| Integration Design | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |
| Integration Build (OIC / API) | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Cutover Planning | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |
| Cutover Execution Monitoring | APC-3 (AI-Augmented) | APC-3 (AI-Augmented) |
| Hypercare / Post Go-Live Support | APC-2 (AI-Assisted) | APC-2 (AI-Assisted) |

# Component 3 — The AI-Adjusted Effort Formula

🔢 The Core Formula AI-Adjusted Effort = (Base Effort × AI Productivity Factor) + AI Overhead Where: Base Effort = Traditional benchmark hours for the activity (from historical data) AI Productivity = 1 – APC Reduction % (e.g. APC-3 at 55% reduction = factor of 0.45) Factor AI Overhead = Tool setup + Prompt engineering + Output validation hours

## AI Productivity Factors by APC Level

| APC Level | Effort Factor (apply to Base) | How to read it |
| --- | --- | --- |
| APC-1 Fully Human | 1.00 | No reduction. Use traditional benchmark as-is. |
| APC-2 AI-Assisted | 0.60 – 0.75 | Human leads; AI saves 25–40% of the effort. |
| APC-3 AI-Augmented | 0.35 – 0.55 | AI does heavy lifting; human validates. 45–65% savings. |
| APC-4 AI-Led | 0.20 – 0.35 | AI executes autonomously. 65–80% savings. |

## AI Overhead — New Effort Categories to Always Add

These are net-new effort items that do not exist in traditional estimates. Omitting them leads to budget overruns during delivery.

| Overhead Category | When to Add | Typical Hours | Notes |
| --- | --- | --- | --- |
| AI Tooling Setup & Configuration | Once per program | 80–150 hrs | GitHub Copilot, Opkey, AI migration tools, prompt libraries |
| Team AI Enablement / Training | Once per program (first 4 weeks) | 4–8 hrs per person | Hands-on ramp-up; declines to near zero by week 6 |
| Prompt Engineering (per workstream) | Per major workstream | 8–20 hrs | Designing, iterating, and documenting effective prompts |
| AI Output Validation (QA gate) | Every AI-generated artifact | 15–20% of saved hours | Human review of code, config, mappings, test cases |
| AI Model Governance | Ongoing throughout program | 2–4 hrs/week | Ensuring AI tools comply with data privacy and security rules |
| Prompt/Tool Iteration (learning curve) | First 6 weeks of program | 10–15% of AI-generated effort | Reducing as team expertise grows |

# Component 4 — Greenfield vs Brownfield Estimation Differences

Greenfield (new implementation from scratch) and Brownfield (upgrade, migration, or reimplementation of an existing system) have fundamentally different AI leverage profiles. Understanding these differences is essential to avoid mis-estimating.

## Greenfield Implementation — AI Estimation Profile

In a greenfield program, there is no legacy system to analyse, no existing customisations to remediate, and no data to migrate from a complex source. The primary effort drivers are configuration volume, extension complexity, integration count, and data load volume.

🟢 Greenfield — Where AI Gives the Biggest Gains → Configuration: AI can accelerate FSM/setup data entry dramatically — the work is largely template-driven, ideal for AI-augmented execution. → Integration Build: OIC/REST integrations follow patterns AI handles very well — scaffolding, error handling, mapping. → Test Automation: No legacy test scripts to convert; AI builds the suite from scratch using process docs. → Documentation: AI generates FDDs, TDDs, config workbooks from workshop outputs in near real-time. → Data Load (FBDI/HDL): AI maps source files to load templates and generates validation scripts automatically.

🔴 Greenfield — Where AI Has Limited Impact → Business Process Design Workshops: These require human facilitation, organisational knowledge, and stakeholder trust. → Solution Architecture Decisions: Choosing between standard vs. custom, module sequencing, and integration patterns needs experienced architects. → Change Management & Training Delivery: Human-centred activities where AI can assist (content creation) but not lead. → UAT Coordination: Business users driving UAT scenarios, sign-off cycles, and defect prioritisation remain human-led.

| ❌ Traditional Greenfield Estimate Structure | ✅ AI-Augmented Greenfield Estimate Structure |
| --- | --- |
| Single effort figure per task | Base effort × APC productivity factor per task |
| Same benchmark for all consultants regardless of AI use | AI-tier resource rates (AI-enabled consultant = higher rate, lower hours) |
| No AI tool costs or overhead | AI tooling costs + overhead hours explicitly budgeted |
| Linear: more objects = proportionally more effort | Sub-linear: AI creates economies of scale at volume |
| Testing estimated as % of dev effort (typically 25–30%) | Testing estimated independently using AI test velocity benchmarks |
| Documentation estimated as % of total (typically 10–15%) | Documentation largely collapsed into AI overhead category |
| Fixed team size × fixed duration = estimate | Smaller team × faster duration = same or better outcome |

## Brownfield — Upgrade / Migration Estimation Profile

Brownfield programs are fundamentally different because AI has a whole new class of high-value activities it can perform: analysing the existing system. Legacy code analysis, customisation impact assessment, data profiling, and parallel run validation are activities that barely exist in greenfield — and AI transforms all of them in brownfield.

🟢 Brownfield — Where AI Gives the Biggest Gains (Different from Greenfield) → Legacy Code / Repository Analysis: AI reads thousands of custom objects and classifies them for upgrade impact in hours, not weeks. → Upgrade Impact Assessment: AI compares source vs. target release, flags deprecated APIs, changed data models, and incompatible constructs. → Data Profiling: AI analyses source system data quality, volume, and anomalies before migration planning begins. → Source-to-Target Mapping: AI learns the source schema and suggests FBDI/HDL/RICE mappings — the most time-intensive brownfield data activity. → Parallel Run Validation: AI compares results (payroll outputs, financial postings, reports) between old and new system at scale. → Regression Suite Rebuild: AI rebuilds test scripts for the target system from the existing business process library.

🔴 Brownfield — Additional Complexity AI Does NOT Remove → Business process redesign decisions ("should we fix the bad process or replicate it?") → Organisational change management — users are moving FROM a known system they trust. → Data cleanse decision-making: AI identifies the problems, humans decide how to resolve them. → Complex customisation remediation where deep business logic understanding is required. → Cutover go/no-go decisions and risk management remain with experienced program leaders.

| ❌ Traditional Brownfield Estimate Structure | ✅ AI-Augmented Brownfield Estimate Structure |
| --- | --- |
| Discovery phase: 8–12 weeks of manual analysis | Discovery phase: 3–5 weeks with AI system analysis |
| Custom object inventory: manual spreadsheet exercise | Custom object inventory: AI-generated in days with risk scoring |
| Data mapping: human-led workshops + analyst time | Data mapping: AI-suggested 80%+ of mappings; human reviews exceptions |
| Test scripts: rebuilt from scratch or carried forward manually | Test scripts: AI rebuilds suite from existing business process docs |
| Parallel run: weeks of manual reconciliation | Parallel run: AI comparison engine; human investigates flagged variances |
| Upgrade impact: consultant expertise + manual code review | Upgrade impact: AI-generated report per object; human validates decisions |
| Documentation: recreated from scratch | Documentation: AI extracts from existing system and reformats |

# Component 5 — Updated Sizing Approaches for Oracle Programs

Traditional sizing methods must be updated for AI delivery. The table below shows how each traditional sizing technique evolves in an AI-augmented model.

## 5.1  Object-Based Sizing (WRICEF / RICE / CEMLI) — Updated

This is the most common Oracle sizing technique. The object count logic is unchanged — what changes is the effort benchmark per object type, and how complexity is classified.

| Object Type | Traditional Hours (H / M / L) | AI-Adjusted Hours (H / M / L) | AI Participation |
| --- | --- | --- | --- |
| Report (BI Publisher / OTBI / SQR) | 40 / 24 / 12 hrs | 18 / 10 / 5 hrs | APC-3 |
| Interface (Inbound / OIC) | 80 / 50 / 24 hrs | 35 / 22 / 10 hrs | APC-3 |
| Conversion / Data Load (FBDI / HDL) | 120 / 80 / 40 hrs | 48 / 30 / 14 hrs | APC-3 to 4 |
| Extension (VBCS / OAF / eScript) | 100 / 60 / 30 hrs | 45 / 25 / 12 hrs | APC-2 to 3 |
| Form / Workflow Configuration | 40 / 24 / 10 hrs | 20 / 12 / 5 hrs | APC-3 |
| PL/SQL Package / Procedure | 60 / 36 / 18 hrs | 24 / 14 / 7 hrs | APC-3 |
| PeopleCode / App Engine | 60 / 36 / 18 hrs | 26 / 15 / 8 hrs | APC-3 |
| OIC Integration Flow | 70 / 44 / 22 hrs | 28 / 16 / 8 hrs | APC-3 |
| Test Script (per test case) | 4 / 2.5 / 1.5 hrs | 1.5 / 0.8 / 0.4 hrs | APC-3 to 4 |
| FDD / TDD (per document) | 12 / 8 / 4 hrs | 4 / 2.5 / 1.5 hrs | APC-3 |

📌 Important Caveat on Object Benchmarks The AI-adjusted hours above assume a consultant with 3+ months of AI tooling experience and a well-maintained prompt library. Apply a Learning Curve Multiplier of 1.15–1.25 for the first program a team delivers with AI. Complexity classification itself remains unchanged — AI does not change WHAT is complex, only HOW FAST it can be built.

## 5.2  Phase-Level Effort Distribution — How It Shifts

AI does not reduce all phases equally. The effort distribution across phases shifts significantly. This has important implications for program planning and resource loading.

| Program Phase | Traditional % of Total | AI-Era % of Total | Direction of Change |
| --- | --- | --- | --- |
| Discovery / Fit-Gap / Blueprint | 12–16% | 10–14% | ↓ Slight reduction (AI accelerates analysis) |
| Solution Architecture & Design | 8–12% | 10–14% | ↑ Slight increase (more time on design decisions) |
| Configuration & Build | 30–40% | 25–32% | ↓ Significant reduction (AI in build execution) |
| Data Migration | 15–20% | 10–14% | ↓ Large reduction (AI-led mapping/validation) |
| Testing (SIT / Regression / UAT) | 18–25% | 14–18% | ↓ Significant reduction (AI test execution) |
| AI Tooling, Overhead & Governance | 0% | 5–8% | ↑ Net new category (did not exist before) |
| Change Management & Training | 6–10% | 8–12% | ↑ Increase (more emphasis needed with AI-change) |
| Cutover & Go-Live | 4–6% | 4–6% | → Largely unchanged |

Key insight: Design and Change Management phases grow in relative importance in the AI era. AI compresses execution but humans still need to make the right decisions and bring the organisation along. Under-investing in these phases is the #1 risk in AI-accelerated Oracle programs.

# The AI-Augmented Estimation Process — Step by Step

How to actually build the estimate in practice, for both Greenfield and Brownfield Oracle programs.

## Step 1 — Establish the Scope Inventory

- Greenfield:  Count modules in scope, configuration objects, integrations, reports, extensions, and data migration entities.

- Brownfield:  Run AI-assisted discovery to auto-inventory existing customisations, data entities, interfaces, and reports in the source system.

  - Use AI tools for brownfield discovery — this step itself is AI-enabled and takes 30–50% less time than traditional manual discovery.

## Step 2 — Classify Every Activity by APC Level

- Apply the APC 1–4 classification to every SDLC activity and object type.

- Mark APC-1 activities as "Protected" — these do not get AI productivity adjustments and must retain full traditional benchmark hours.

- This is the most important estimating decision — misclassifying a business process design workshop as APC-3 will cause delivery failure.

## Step 3 — Apply AI Productivity Factors to Base Benchmarks

- Start with your organisation's existing benchmark table (RICE hours, phase % splits).

- Apply the APC productivity factor to each line item.

- Do NOT apply a blanket factor across the whole estimate — AI impact is not uniform.

## Step 4 — Add AI Overhead

- Add AI tooling setup hours (one-time, first 6–8 weeks of program).

- Add team AI enablement hours per resource.

- Add output validation hours (15–20% of hours saved by AI per workstream).

- Add prompt engineering time per major workstream.

- Add ongoing AI governance hours for the program duration.

## Step 5 — Apply Programme-Level Adjusters

These are multipliers applied to the total AI-adjusted estimate before presenting:

| Adjuster | Condition | Multiplier |
| --- | --- | --- |
| AI Learning Curve | Team has < 3 months experience with AI delivery tooling | × 1.15 – 1.25 (first 8 weeks only) |
| AI Tool Maturity | Using unproven or recently released AI tools | × 1.10 – 1.15 (risk buffer) |
| Data Complexity Premium | Source system data quality is poor / unknown | × 1.20 – 1.35 on data migration workstream |
| Regulatory / Security Constraint | AI tools restricted by client data policy (e.g. on-premise only, no cloud AI) | × 1.20 – 1.30 (reduces AI participation) |
| Highly Bespoke Customisations | Deep, unique business logic with no pattern AI can recognise | × 1.00 (APC-1 — no AI factor applied) |
| Offshore AI Delivery | AI-enabled offshore team with strong tooling | × 0.85 – 0.90 (AI + offshore compound) |

## Step 6 — Sanity Check Against Outcome-Based Benchmarks

In the AI era, a new cross-check is available: outcome benchmarks. Instead of only checking "are my hours per task reasonable?", also check:

- Conversion entities per data migration consultant per week: traditionally 1–2 entities; AI-era benchmark is 3–5 entities per week.  →

- RICE objects per developer per sprint: traditionally 2–3 objects; AI-era benchmark is 5–8 objects per sprint.  →

- Test cases created per test analyst per day: traditionally 8–12; AI-era benchmark is 25–40 (with AI generation).  →

- Test cases executed per day (automated): no human limit — AI runs thousands overnight.  →

If your estimate implies velocity lower than these benchmarks, you are over-estimating. If it implies velocity significantly higher, you may be under-estimating AI overhead.

# Estimation Models by Program Type

The following shows how the model applies differently to each Oracle program type across Greenfield and Brownfield scenarios.

## Oracle Fusion Cloud — Greenfield Implementation

| Work Package | Basis of Estimate | APC Level | Key AI Lever | Example: 5-module Finance Program |
| --- | --- | --- | --- | --- |
| Discovery & Blueprinting | Fixed phase + workshops | APC-1 / 2 | AI meeting notes → process maps | 300–500 hrs |
| FSM Configuration | Per module × config density | APC-3 | AI pre-populates FSM from workbook | 400–700 hrs |
| OTBI / BIP Reports | Per report × complexity | APC-3 | AI generates from data model + spec | 200–400 hrs |
| OIC Integrations | Per integration × complexity | APC-3 | AI scaffolds flows + error handling | 400–800 hrs |
| FBDI Data Load | Per entity × volume × quality | APC-3/4 | AI maps, transforms, validates | 500–900 hrs |
| SIT / Regression Testing | Per test case (AI velocity) | APC-4 | AI generates + executes + triages | 300–500 hrs |
| UAT Support | Fixed phase | APC-2 | AI defect categorisation + retests | 200–350 hrs |
| AI Tooling & Overhead | Fixed (per program) | Overhead | Setup, prompts, validation, governance | 150–250 hrs |
| Change Mgmt & Training | Fixed + training units | APC-1/2 | AI content generation; human delivery | 300–500 hrs |
| TOTAL (Indicative) |  |  |  | 2,750 – 4,900 hrs |

Traditional estimate for the same scope: approximately 5,500 – 9,000 hrs. AI-adjusted estimate represents a 42–50% reduction.

## Oracle EBS/PeopleSoft — Brownfield Upgrade

| Work Package | Basis of Estimate | APC Level | Key AI Lever | Example: R12 → 12.2.x Upgrade |
| --- | --- | --- | --- | --- |
| Discovery & Impact Analysis | AI-automated system scan + human review | APC-3 | AI inventories custom objects + risk scores | 150–250 hrs (was 400–600) |
| Upgrade Impact Report | Per custom object (AI-generated) | APC-3 | AI compares source vs target APIs/schema | 80–150 hrs (was 250–400) |
| RICE Remediation | Per object × impact level | APC-2/3 | AI refactors code to new APIs | 500–900 hrs (was 1,200–2,000) |
| Configuration Delta | AI comparison + human sign-off | APC-3 | AI compares config tables source vs target | 100–180 hrs (was 200–350) |
| Data Migration / Cleanse | Per entity × quality score | APC-3/4 | AI profiles, maps, validates | 300–500 hrs (was 600–900) |
| Regression Test Suite Rebuild | AI rebuilds from process library | APC-3/4 | AI generates + executes full regression | 200–350 hrs (was 600–1,000) |
| UAT + Parallel Run | Fixed phase + AI comparison | APC-2/4 | AI runs parallel comparison at scale | 300–500 hrs (was 500–800) |
| AI Tooling & Overhead | Fixed per program | Overhead | Setup, validation, governance | 120–200 hrs |
| TOTAL (Indicative) |  |  |  | 1,750 – 3,030 hrs |

Traditional estimate for the same scope: approximately 4,000 – 7,000 hrs. AI-adjusted estimate represents a 45–55% reduction.

# How Estimation Feeds Commercial Models in the AI Era

Estimating fewer hours creates a commercial tension: clients expect lower prices (because AI saves effort), while delivery partners want to retain margin (because AI tooling costs money). The new estimation approach must address this head-on.

## The Three Commercial Model Options

| Commercial Model | How Estimate Is Used | Who Benefits from AI Savings | Best Fit |
| --- | --- | --- | --- |
| Time & Materials (T&M) | Estimate sets resource plan; actuals billed. Client pays for actual AI-adjusted hours. | Client gets lower bill if AI performs well | Low-complexity programs; clients who want transparency |
| Fixed Price | AI-adjusted estimate sets the price. Delivery partner absorbs risk and upside of AI performance. | Delivery partner captures upside of AI outperforming estimate | Well-defined scope; mature AI tooling; strong templates |
| Outcome / Value-Based | Price tied to delivered outcomes (system live, SLA achieved, defect rate). Effort is internal. | Both parties share value created | Large programs; strong partnership; willingness to co-invest |

💡 Recommended Approach For most Oracle programs in 2025–2027, recommend a Hybrid model: → Fixed price for AI-led workstreams (data migration, regression testing, documentation) — these are well-defined, AI handles predictably, you can absorb the risk and capture upside. → T&M with a capped estimate for human-led workstreams (blueprinting, change management, UAT) — these vary by client behaviour and cannot be fixed-priced responsibly. Offer the client a single blended price that reflects this structure without revealing the internal split.

## How to Present AI-Adjusted Estimates to Clients

Do NOT present estimates as simply "we are using AI so it costs less." Clients want to understand where the savings come from and be assured that quality is maintained. Use this structure:

- Lead with the outcome:  Show the client what they get (working system, migrated data, test coverage) — not just how many hours it takes.

- Show the AI layer:  Explicitly call out which activities are AI-augmented, and what validation ensures quality (e.g. "all AI-generated code is reviewed by a senior architect").

- Present the AI overhead:  Do not hide the tooling, setup, and validation costs. Clients trust transparent estimates more than suspiciously low ones.

- Offer a comparison:  Show the traditional estimate vs. the AI-adjusted estimate side-by-side. Let the client see they are getting the same scope for less.

- Provide a contingency:  Include an AI performance contingency of 5–10% — if AI tools underperform expectations, this absorbs the impact without a change request.

# Estimation Quick Reference — AI-Augmented Oracle Programs

GREENFIELD IMPLEMENTATION

| Step | Action | Greenfield Specific Note |
| --- | --- | --- |
| 1 | Inventory scope (modules, objects, integrations, data entities) | Use Oracle Cloud readiness tools + AI to auto-size configuration depth |
| 2 | Apply APC classification per activity type | Config, reports, integrations, data load → mostly APC-3; design, UAT → APC-1/2 |
| 3 | Apply productivity factors to base benchmarks | See updated RICE/CEMLI benchmark table in Section 5.1 |
| 4 | Add AI overhead (fixed + per-workstream) | Budget ~150–250 hrs for a medium-sized greenfield program |
| 5 | Apply learning curve multiplier if team is new to AI delivery | × 1.15 for first 8 weeks; no multiplier from week 9 onwards |
| 6 | Sanity check against AI velocity benchmarks | Target 5–8 RICE/sprint; 3–5 data entities/week; 25–40 test cases/analyst/day |
| 7 | Adjust commercial model (Fixed / T&M / Hybrid) | Hybrid recommended: fix AI-led workstreams, T&M cap human-led workstreams |

BROWNFIELD — UPGRADE / MIGRATION

| Step | Action | Brownfield Specific Note |
| --- | --- | --- |
| 1 | Run AI-assisted discovery on source system | This step itself is AI-enabled — budget 150–250 hrs (vs 400–600 traditional) |
| 2 | Classify custom objects by upgrade impact (AI-generated) | High / Medium / Low / Retire — AI does the classification, human validates |
| 3 | Apply APC to remediation, not just development | Legacy code analysis and impact assessment are APC-3 activities |
| 4 | Size data migration based on AI-profiled source data quality | Poor quality data = higher effort even with AI; budget data quality contingency |
| 5 | Build regression suite cost using AI test velocity benchmarks | AI regenerates test suite faster than inheriting old manual scripts |
| 6 | Add parallel run / reconciliation effort using AI comparison model | AI comparison engine reduces parallel run from weeks to days |
| 7 | Apply Data Complexity Premium if source quality is unknown | × 1.20–1.35 on data workstream until profiling confirms quality level |

AI-Augmented Estimation POV — Oracle Programs | July 2026