POINT OF VIEW — ADDENDUM II

Sizing Volumetrics in the AI Era:

Greenfield vs Brownfield Oracle Programs

Why sizing drivers, volumetric inputs, and measurement techniques are fundamentally different

July 2026

# The Core Difference: What You Are Measuring

In Greenfield, you are measuring the VOID — what needs to be built from scratch. In Brownfield, you are measuring the EXISTING SYSTEM — what already exists and how much of it needs to change, move, or be retired. These require completely different inputs, different data collection techniques, and different volumetric parameters.

⚡ The Fundamental Distinction GREENFIELD sizing answers: "How much do we need to CREATE?" → Drivers: modules in scope, process complexity, object count, data volume to load BROWNFIELD sizing answers: "How much exists, how much must CHANGE, and how much do we CARRY FORWARD?" → Drivers: existing customisation footprint, data quality, delta between source and target, volume of legacy objects to analyse, remediate, or retire These are not the same question. Applying Greenfield sizing logic to a Brownfield program is one of the most common and costly estimation mistakes in Oracle delivery.

## High-Level Sizing Component Comparison

| Sizing Component | Greenfield | Brownfield |
| --- | --- | --- |
| Sizing Component | Greenfield | Brownfield |
| Primary source of scope | Business requirements & process scope | Existing system — customisations, data, config |
| Discovery effort | Low — driven by workshops | High — system analysis is itself a major workstream |
| Object count basis | Future-state design decisions | Inventory of existing RICE/CEMLI/repository objects |
| Data sizing basis | Volume of master & transactional data to load | Source data volume + quality + migration complexity |
| Configuration sizing | Modules × setup density × process complexity | Delta between source config and target config |
| Testing basis | Process coverage × test scenario count | Regression coverage of existing footprint + delta |
| Integration sizing | Number of new interfaces × complexity | Existing interfaces: retire / rebuild / carry forward |
| Change complexity | People moving TO a new system | People moving AWAY FROM a known system they trust |
| AI's biggest sizing lever | Accelerating build of net-new objects | Analysing & classifying the existing system's footprint |

PART A — GREENFIELD SIZING VOLUMETRICS

## What Drives Greenfield Scope

In a Greenfield implementation, you have no existing system to constrain or inform you. Scope is defined entirely by what the business wants to achieve. The sizing inputs come from requirements, process blueprints, and design decisions made during the program.

### Greenfield Sizing Input #1 — Module & Process Scope

The first and most important sizing lever in Greenfield is: which modules are in scope and how many end-to-end business processes do they cover?

| Parameter | What to Count | How AI Changes Collection | Impact |
| --- | --- | --- | --- |
| Volumetric Parameter | What to Count | How AI Changes Collection | Effort Impact |
| Modules in scope | Count of Oracle modules being implemented (e.g. AP, AR, GL, Procurement, HCM Core) | Oracle Cloud Readiness AI tool auto-maps module → configuration task count | Baseline effort anchor for configuration |
| Level-3 / Level-4 processes | Business processes within each module (e.g. within AP: Invoice Processing, Payment Runs, Expense Management) | AI reads process libraries and maps to Oracle standard processes | Each process = test scenarios, training units, config tasks |
| Process variants | How many variants of each process (e.g. 3 legal entities, 2 invoice types, 4 approval hierarchies) | AI identifies variants from workshop transcripts and org data | Multiplier on base process effort — most underestimated input |
| Localisation requirements | Countries × local statutory / tax requirements | AI queries Oracle localisation coverage by country | Each country adds fixed overhead to config and compliance testing |
| User roles / personas | Distinct user types who interact with the system | AI analyses job descriptions to cluster into Oracle role profiles | Drives security design, training units, and UAT participant count |

### Greenfield Sizing Input #2 — Configuration Density

Configuration is sized by MODULE × COMPLEXITY TIER. Not all modules are equal — some Oracle modules have hundreds of setup tasks; others have dozens. Complexity tier reflects how deeply the standard configuration needs to be customised to fit the business.

| Tier | Definition | Examples | Sizing Multiplier |
| --- | --- | --- | --- |
| Configuration Tier | Definition | Oracle Examples | Sizing Multiplier |
| Tier 1 — Standard Adopt | Use Oracle delivered setup with minimal changes. Business adopts Oracle's way of working. | Fusion Expenses, basic AP/AR | 1.0× (baseline) |
| Tier 2 — Configured | Oracle standard with significant setup customisation: approval workflows, flexfields, lookups, process orchestration. | Fusion GL with multi-ledger, Procurement with approval hierarchies | 1.5–2.0× |
| Tier 3 — Extended | Configuration + extensions: VBCS pages, Groovy scripts, custom OIC integrations, BIP reports beyond standard. | Complex HCM with custom payroll rules, Complex SCM with custom fulfilment logic | 2.5–3.5× |
| Tier 4 — Highly Bespoke | Significant custom development required. Standard product does not adequately cover the business need. | Rare in Fusion; more common in ECC/PeopleSoft implementations | 4.0–6.0× |

### Greenfield Sizing Input #3 — Extension Object Inventory (WRICEF)

Extensions are sized by counting and classifying WRICEF objects (Workflows, Reports, Interfaces, Conversions, Extensions, Forms). In Greenfield, these are determined by the gap between what Oracle delivers and what the business needs.

| Type | Volume Determination | Complexity Classification | AI Lever |
| --- | --- | --- | --- |
| Object Type | How Volume is Determined (Greenfield) | Complexity Classification | AI Sizing Lever |
| W — Workflow / Approval | Count approval flows not covered by Oracle standard workflow configurator | H: multi-level, conditional; M: standard multi-level; L: simple | AI reads org chart + approval policy → suggests workflow count |
| R — Reports | Count reports needed beyond Oracle standard: operational, regulatory, management | H: complex multi-data source; M: single module; L: simple list | AI maps report catalogue to Oracle delivered vs gap reports |
| I — Interfaces (Inbound/Outbound) | Count system-to-system integrations with 3rd party and legacy systems | H: complex transformation, real-time; M: batch with transformation; L: simple batch | AI maps integration landscape diagram to OIC template count |
| C — Conversions | Count master data entities + transactional history to load | Sized separately — see Data Migration volumetrics below | AI auto-generates FBDI template inventory from data model |
| E — Extensions / Enhancements | Custom pages, Groovy scripts, VBCS apps to add functionality | H: new page / complex logic; M: field add + validation; L: simple field default | AI analyses requirements gap list → extension type classification |
| F — Forms / Screens | In Fusion context: custom VBCS forms for unique data capture | H: complex multi-section; M: standard form; L: simple single field | AI generates VBCS form from UI wireframe or data model |

### Greenfield Sizing Input #4 — Data Migration Volumetrics

In Greenfield, data migration means loading master data and any opening balances or transactional history from source systems (which may be spreadsheets, legacy ERP, or disparate databases) into the new Oracle system.

| Entity Type | Volume Metric | Complexity Drivers | Sizing Guide |
| --- | --- | --- | --- |
| Data Entity Type | Volume Metric | Complexity Drivers | Typical Greenfield Data Migration Sizing Parameters |
| Master Data — Customers | Record count | Deduplication need, address validation, hierarchy | <5K = Low; 5K–50K = Medium; >50K = High |
| Master Data — Suppliers | Record count | PO history, bank details, tax registrations | <2K = Low; 2K–20K = Medium; >20K = High |
| Master Data — Items / Products | Record count × attribute richness | UOM, pricing, category hierarchy depth | <10K SKUs = Low; 10K–100K = Medium; >100K = High |
| Master Data — Chart of Accounts | Account code count × mapping complexity | Restructuring required vs direct map | Direct map = Low; Restructure = High (× 2.5) |
| Master Data — Employees / Workers | Headcount × countries | Assignment history, payroll elements, benefits | Simple: 2.0 hrs/100 employees; Complex: 6.0 hrs/100 |
| Opening Balances (Finance) | Ledger count × period | Balancing requirements, intercompany | 1 ledger = Low; Multi-ledger multi-currency = High |
| Transactional History | Year count × transaction volume | Archiving vs migrating; reporting need | Each year of history adds 30–40% to base conversion effort |
| Reference / Config Data | Setup table count | Validation rules, lookup dependencies | Usually bundled into Configuration workstream |

### Greenfield Sizing Input #5 — Testing Volumetrics

Testing in Greenfield is sized from the process scope — you test what you have designed. The primary inputs are process count, variant count, and integration point count.

| Test Type | Volume Basis | Traditional Rate | AI-Adjusted Rate |
| --- | --- | --- | --- |
| Testing Type | Greenfield Volume Basis | Traditional Rate | AI-Adjusted Rate |
| SIT Test Cases | # Level-3 processes × average scenarios per process (typically 3–5) | 1.5–2.5 hrs design + 0.8 hrs execute per case | 0.5–0.8 hrs design (AI gen) + AI executes |
| Integration Test Cases | # interfaces × scenarios per interface (happy path + 3 error paths) | 3–5 hrs per interface test case | 1.0–1.5 hrs (AI generates from OIC spec) |
| Regression (after config changes) | Full process scope — all in-scope L3 processes | Full cycle: 4–8 weeks manual | AI-driven: 3–5 days overnight runs |
| UAT Test Cases | # business scenarios × # user roles (typically 60–70% of SIT scope) | Facilitated by delivery team; user execution time separate | AI generates test scripts; user validates outcomes |
| Performance Test Cases | # critical transaction types × volume thresholds | Scripting: 40–80 hrs; Execution: 1–2 weeks | Scripting: 15–25 hrs (AI); Execution: unchanged |
| Data Migration Validation | # conversion entities × validation rule count | Manual reconciliation: 8–20 hrs/entity | AI comparison: 1–3 hrs/entity |

PART B — BROWNFIELD SIZING VOLUMETRICS

## What Drives Brownfield Scope

In Brownfield, scope is not defined by what you want to build — it is defined by what already exists. You must first understand the current system deeply before you can size the effort to change it. This makes discovery itself a critical, effort-heavy, and often underestimated workstream.

🔍 The Brownfield Discovery Problem Every Brownfield program starts with a fundamental uncertainty: nobody fully knows what they have. The application has evolved over years with different teams, different consultants, and undocumented changes. Documentation is outdated. Key people have left. Technical debt has accumulated. Sizing a Brownfield program before discovery is completed is one of the highest-risk activities in Oracle delivery. AI-assisted discovery is the single most valuable thing you can do to de-risk a Brownfield estimate.

### Brownfield Sizing Input #1 — Existing System Footprint Inventory

Before anything else, you must inventory what exists. This is a volumetric exercise in itself — and the foundation of all subsequent sizing.

| What to Inventory | Traditional Approach | AI-Assisted Approach | Output |
| --- | --- | --- | --- |
| What to Inventory | How Traditionally Done | How AI Changes This | Output Used For |
| Custom code objects (RICE/CEMLI count by module) | Manual review of system, developer interviews, code repository audit: 4–8 weeks | AI scans codebase / repository and generates inventory with classification in days | Primary driver of upgrade/remediation effort sizing |
| Configuration delta (custom vs standard) | Manual comparison of setup tables vs Oracle delivered baseline | AI compares source instance config tables against delivered baseline automatically | Drives configuration rework effort sizing |
| Report inventory | Manual catalogue from report library + user interviews | AI extracts report metadata from system and classifies by usage frequency | Identifies candidates to retire vs migrate — affects sizing significantly |
| Interface / integration inventory | Interface catalogue from technical team; often incomplete | AI reads integration middleware logs and system logs to identify all active interfaces | Drives integration rebuild/retire decision and effort |
| User count and role structure | HR data + security team input | AI reads security configuration and job data to cluster roles | Drives security redesign and training sizing |
| Transaction volumes (by process) | Manual pull from DBA; often estimated | AI queries database statistics and generates volume report by module | Critical for performance testing sizing and data migration scoping |
| Data quality baseline | Manual data profiling: 4–8 hrs per entity | AI profiles all entities simultaneously in hours | Adjusts data migration complexity multipliers and cleanse effort |
| Usage analytics (active vs dormant features) | None — almost never done traditionally | AI mines application access logs to identify what is actually used vs configured but unused | Allows retirement of dormant customisations — reduces scope |

### Brownfield Sizing Input #2 — The Custom Object Classification Matrix

Once inventoried, every custom object must be classified into one of four disposition categories. This classification is the most important sizing decision in a Brownfield program — it determines 60–70% of the total effort.

| Disposition | Definition | Effort | AI Role |
| --- | --- | --- | --- |
| Disposition | Definition | Effort Implication | AI Role in Classification |
| RETIRE | Custom object no longer needed. Standard product now covers the requirement, or the requirement no longer exists. | Zero build effort. Some effort for retirement validation and user communication. | AI checks if delivered functionality in target release covers the custom object's purpose. Recommends retire candidates. |
| ADOPT STANDARD | Retire the custom object and adopt the Oracle standard equivalent. May require business process change. | Configuration effort only — no custom development. Change management effort increases. | AI maps custom object functionality to Oracle standard feature set. Flags where business process change is needed. |
| REBUILD | Custom object must be recreated in the target platform using new tools (e.g. eScript → OIC, OAF → VBCS, SQR → BIP). | Full development effort at AI-adjusted rates. Logic must be re-understood and re-implemented. | AI reads existing code and generates specification + first-cut implementation in target technology. |
| CARRY FORWARD | Custom object is technically compatible with target release and requires only minor remediation (e.g. API updates, namespace changes). | Remediation effort only — typically 20–40% of a full rebuild. | AI performs compatibility check and identifies specific lines of code requiring change. Generates remediation diff. |

📊 Why This Classification Changes Everything A program with 500 custom objects where 40% are Retire/Adopt Standard is fundamentally different from one where 90% are Rebuild. The effort difference can be 3–4× for the same raw object count. Traditional estimates often default to "Rebuild everything" because classification was too hard to do early. AI-assisted classification can be done in the discovery phase — changing the estimate foundation from "worst case" to "reality-based". Example: A Siebel 8.1 program with 800 repository objects traditionally sized as 800 rebuilds. AI classification reveals: 220 Retire ¦ 180 Adopt Standard ¦ 280 Rebuild ¦ 120 Carry Forward. Actual rebuild effort = 35% of original estimate.

### Brownfield Sizing Input #3 — Data Migration Volumetrics (Very Different from Greenfield)

Brownfield data migration is fundamentally more complex than Greenfield. You are not loading data from spreadsheets or a simple source — you are extracting, transforming, and validating data from a complex, years-old production system with all its accumulated inconsistencies.

| ❌ Greenfield Data Migration Sizing | ✅ Brownfield Data Migration Sizing |
| --- | --- |
| Count of entities to load | Count of entities + count of entities to cleanse + count of entities to archive vs migrate |
| Source: spreadsheets, simple extract | Source: complex ERP with years of transactions, duplicates, inactive records, structural inconsistencies |
| Mapping: source fields → FBDI template | Mapping: source ERP schema → transformation logic → target schema (often requires data model translation) |
| Quality: assumed clean or user-managed | Quality: must be profiled, scored, and remediated before migration — quality drives effort, not just volume |
| History: usually load current-state only | History: decision needed on how many years of history to migrate vs archive (each year = significant effort) |
| Validation: check loaded vs source spreadsheet | Validation: reconcile migrated data against source system financials, headcounts, inventory at period level |
| Runs: typically 3–4 mock runs + final | Runs: typically 5–8 mock runs for complex systems with incremental cleanse cycles between runs |
| Data cleanse: user's responsibility pre-load | Data cleanse: joint exercise — AI profiles, team cleanses, AI validates — explicitly in scope |

### Brownfield Data Migration — Specific Volumetric Parameters

| Parameter | What to Measure | Why Different in Brownfield | AI Tool |
| --- | --- | --- | --- |
| Volumetric Parameter | What to Measure | Why It Is Different in Brownfield | AI Tool |
| Record count by entity | Accounts, suppliers, items, employees, open transactions | Same as Greenfield BUT must exclude inactive/duplicate/invalid records first | AI deduplication and status classification |
| Data quality score (per entity) | % of records passing validation rules before migration | Critical Brownfield input — does not exist in Greenfield. Quality score drives cleanse effort (the biggest wildcard). | AI data profiler: scores each entity 0–100% quality |
| Duplication rate | % of records that are duplicate or near-duplicate | ERP systems accumulate years of duplicates. High dedup rate = significant pre-cleanse effort. | AI matching engine identifies duplicates by entity type |
| Historical data period | Years of transactional history to be migrated | Each additional year multiplies extraction, transformation, and validation effort | AI classifies transactions by age and reference frequency |
| Source schema complexity | Number of source tables + relationships per entity | Complex ERP schemas (EBS, PeopleSoft) have hundreds of tables per module — each requires mapping | AI reverse-engineers source schema and maps to target |
| Structural recode required | % of master data requiring code structure change (e.g. COA restructure, cost centre rename) | Common in Brownfield upgrades / platform changes. Recoding adds 50–100% to base mapping effort. | AI applies recode rules and validates derivation logic |
| Cutover data delta volume | Volume of transactions between final mock run and go-live | Brownfield-only consideration — must extract and load the "delta" during cutover window | AI automates delta identification and incremental load |
| Reconciliation complexity | Number of control reports and sign-off points required | Finance and HR require period-level reconciliation vs source system before go-live approval | AI comparison engine generates reconciliation pack automatically |

### Brownfield Sizing Input #4 — Testing Volumetrics

Testing in Brownfield is not about testing what you have designed — it is about testing that what you had still works the same way (regression), PLUS testing everything that is new or changed. This creates a dual-layer testing scope that Greenfield does not have.

| Test Type | Greenfield | Brownfield | Key Difference |
| --- | --- | --- | --- |
| Testing Type | Greenfield Basis | Brownfield Basis | Key Difference |
| Functional Testing (SIT) | All in-scope L3 processes (everything is new) | Delta processes only — what has changed in the upgrade / migration | Brownfield SIT scope can be 40–60% of Greenfield if most processes are unchanged |
| Regression Testing | Not applicable — no prior baseline exists | ENTIRE existing process footprint must be re-validated | This is the largest testing cost unique to Brownfield — often larger than SIT |
| Custom Object Testing | Unit test all newly built RICE objects | Unit test rebuilt objects + smoke test carry-forward objects + validate retired objects are truly gone | 3 test passes vs 1 — multiplies test effort significantly |
| Integration Testing | Test all new interfaces | Test rebuilt interfaces + validate retired interfaces are decommissioned + test unchanged interfaces still work | Decommissioning validation is a Brownfield-only cost |
| Data Migration Testing | Validate loaded master data is correct | Validate migrated data MATCHES source system at record level + period-level financial reconciliation | Parallel run is a Brownfield-only activity — can take 6–12 weeks traditionally (2–3 weeks with AI) |
| User Acceptance Testing | Business tests new processes | Business tests changed processes + confirms no regression on unchanged processes they rely on | UAT scope creep is higher in Brownfield — users test "what changed" AND "what should not have changed" |
| Cutover Dress Rehearsal | Simulate go-live data load | Simulate cutover including delta extraction, incremental load, and final reconciliation | Dress rehearsal is far more complex in Brownfield — requires production-like data state |

⚠ The Regression Testing Trap in Brownfield Estimates The single most underestimated workstream in Brownfield programs is regression testing. Traditional Brownfield programs inherit test scripts from the existing system — but those scripts are often outdated, incomplete, or tied to an old test tool that is no longer supported. The choice is: (a) update inherited scripts, or (b) rebuild the regression suite. Traditional approach (a) often costs MORE than building fresh — because updating broken scripts is harder than writing new ones. AI approach: rebuild the regression suite from business process documentation in the AI-augmented rate. This is both faster AND produces a better-quality suite with higher coverage. Brownfield regression suite rebuild using AI: 30–50% of the effort of the traditional update-inherited-scripts approach.

PART C — COMPLETE SIDE-BY-SIDE SIZING COMPARISON

## Master Volumetric Comparison — Greenfield vs Brownfield

The table below is the reference guide for any estimation exercise. For each sizing dimension, it shows the input required, how it differs between Greenfield and Brownfield, and the AI leverage available.

| Sizing Dimension | Greenfield Input | Brownfield Input | AI: Greenfield | AI: Brownfield |
| --- | --- | --- | --- | --- |
| Sizing Dimension | Greenfield Input Required | Brownfield Input Required | AI Leverage: Greenfield | AI Leverage: Brownfield |
| Module Scope | Count of modules in scope | Count of modules IMPACTED by upgrade/migration | Auto-size via Oracle readiness tool | AI identifies impacted modules from change delta |
| Process Count | Level-3 processes in scope per module | Processes that change + processes at regression risk | AI maps requirements to process library | AI compares source vs target process model |
| Process Variants | Variants per process (org, country, entity) | Variants that change + variants that must be regression-tested | AI identifies from workshop transcripts | AI reads existing config to catalogue variants |
| Config Volume | Modules × complexity tier × setup task count | Delta config only + carry-forward validation | AI pre-populates FSM workbook | AI compares source vs target config tables |
| Custom Object Count | Designed WRICEF object list | Inventory of ALL existing custom objects | AI classifies gap list → object types | AI scans system → full inventory in days |
| Custom Object Disposition | N/A — all objects are net-new | Retire / Adopt Standard / Rebuild / Carry Forward split | N/A | AI classifies each object into disposition category |
| Data Entities | Entities to load (master + history) | Entities to migrate + entities to archive + entities to cleanse | AI maps to FBDI/HDL templates | AI profiles, deduplicates, and quality-scores each entity |
| Data Record Counts | Load volume per entity | Gross count → net count after dedup and inactive exclusion | Used for FBDI load time estimation | AI calculates net migrable records after cleansing |
| Data Quality Score | Not measured (assumed adequate) | Quality % per entity — critical sizing input | N/A | AI data profiler generates quality score in hours |
| Historical Data Period | Defined by business (usually 1–3 years) | Existing history in source: may be 10–20 years, decision needed on what migrates | AI sizes FBDI loads by year | AI classifies history by age and reference frequency |
| Integration Count | Count of new interfaces × complexity | Count of existing: retire / rebuild / carry forward | AI scaffolds OIC templates from specs | AI mines logs to inventory active interfaces; classifies disposition |
| Report Count | Count of gap reports needed | Count of existing reports: retire / migrate / rebuild | AI generates BIP/OTBI from data model | AI identifies unused reports via access logs — retire candidates |
| Test Case Count (SIT) | All processes × scenarios per process | Delta processes only × scenarios | AI generates from process docs | AI identifies changed processes from impact assessment |
| Test Case Count (Regression) | N/A | Full existing process footprint × scenarios per process | N/A | AI rebuilds full regression suite from business process library |
| Parallel Run Volume | N/A | Transaction volume for comparison period (payroll, finance) | N/A | AI comparison engine validates at record level automatically |
| User Count / Training Units | Users per role × modules | Users impacted by change × degree of change | AI clusters users into role groups | AI assesses change impact per user group from delta analysis |
| Cutover Delta Volume | N/A — cutover is a one-time load | Volume of transactions between last mock run and go-live | N/A | AI automates delta extract and incremental load |
| Change Management Complexity | Moving to new — users starting fresh | Moving from known — users losing familiar system | AI generates training content from process docs | AI generates change impact assessment from delta analysis |

PART D — PRACTICAL SIZING GUIDE

## How to Collect Sizing Inputs: Greenfield

The following sequence is the recommended approach to gathering sizing inputs for a Greenfield Oracle program estimate. All steps are AI-augmentable.

### Step 1 — Scope Discovery Workshop (Greenfield)

- Collect:  Module list, country list, legal entity list, integration landscape diagram, report catalogue

- Duration:  2–4 days of workshops for a medium-sized program

- AI assist:  AI generates a pre-populated scope template from RFP/SOW documents before the workshop; AI takes structured notes and extracts scope items during workshops

### Step 2 — Process Decomposition (Greenfield)

- Collect:  Level 1–4 process hierarchy per module; number of variants per process

- Duration:  1–2 weeks with functional leads

- AI assist:  AI maps client processes to Oracle standard process library; highlights gaps automatically

### Step 3 — Object Count Estimation (Greenfield)

- Collect:  WRICEF object counts by type and complexity; report count; integration count

- Duration:  3–5 days with solution architects and functional leads

- AI assist:  AI analyses gap between process scope and Oracle standard to estimate object count ranges by type

### Step 4 — Data Migration Scoping (Greenfield)

- Collect:  Entity list, record counts, source system(s), history period, quality assumption

- Duration:  2–3 days; requires data from client

- AI assist:  AI sizes FBDI templates from entity list; generates data migration effort model from entity count and quality inputs

### Step 5 — Build the Estimate (Greenfield)

- Apply:  Configuration complexity tier × module count; WRICEF object benchmarks (AI-adjusted); data entity migration model; process count × testing rate

- AI assist:  AI estimation model applies APC factors automatically once inputs are entered

## How to Collect Sizing Inputs: Brownfield

The Brownfield sizing sequence is fundamentally different — discovery must precede estimation. Attempting to size a Brownfield program without completing discovery leads to estimates that are wrong by 100–200%.

### Step 1 — AI-Assisted System Scan (Brownfield)

- Collect:  Full inventory of custom objects (code, config, reports, interfaces) via AI system scan

- Duration:  1–2 weeks with AI tooling (was 4–8 weeks traditionally)

- AI assist:  AI scans source system, generates inventory with preliminary risk classification and disposition recommendation

  - This step does not require client workshops — it is a technical extract. AI does the heavy lifting.

### Step 2 — AI Data Profiling (Brownfield)

- Collect:  Record counts, quality scores, duplication rates, historical data period, structural issues per data entity

- Duration:  3–5 days with AI data profiling tool (was 2–4 weeks traditionally)

- AI assist:  AI profiles all entities simultaneously, generates quality score report, flags dedup candidates, recommends cleanse priorities

  - Quality score is the single most important Brownfield data sizing input. Without it, estimate is a guess.

### Step 3 — Object Disposition Workshop (Brownfield)

- Collect:  Validated disposition classification (Retire / Adopt Standard / Rebuild / Carry Forward) for all custom objects

- Duration:  3–5 days of focused workshops with functional and technical leads

- AI assist:  AI pre-populates disposition recommendations; humans validate and override. Reduces workshop time by 50%.

  - This workshop is the single most important scoping exercise in a Brownfield program. Do not skip it.

### Step 4 — Delta Analysis (Brownfield)

- Collect:  Configuration delta between source and target; process changes driven by new platform features; integration changes

- Duration:  1–2 weeks with AI comparison tooling (was 3–6 weeks)

- AI assist:  AI compares source vs target config tables, flags differences, and generates delta workbook

### Step 5 — Build the Estimate (Brownfield)

- Apply:  Object count × disposition-weighted effort; data migration model with quality-adjusted effort; regression test suite rebuild estimate; delta SIT estimate

- AI assist:  AI estimation model applies disposition weights and APC factors; flags if data quality contingency should be applied

📌 The Golden Rule of Brownfield Sizing Never build a Brownfield estimate without completing at minimum Steps 1 and 2 above. A Brownfield estimate built without an AI-assisted system scan and data profiling is not an estimate — it is a guess with a spreadsheet attached to it. The cost of running Steps 1 and 2 (typically 3–4 weeks, 150–250 hours with AI tooling) is returned many times over in estimate accuracy. A program that avoids this upfront investment typically discovers the same information during delivery — at program-threatening cost.

Sizing Volumetrics POV — Oracle AI Programs | July 2026