## Cover
ORACLE FUSION CLOUD — DETAILED IMPLEMENTATION ESTIMATOR
Bottom-Up Effort Estimation: Configuration · Customisation · Data Migration · SDLC Phase View
▶ ESTIMATE TYPE SELECTOR
SELECT ESTIMATE TYPE → Enter 'H' for High-Level ¦ 'D' for Detailed H = Use the Oracle Fusion Implementation Estimator (separate workbook — module-level, benchmark-driven) D = Use this workbook — bottom-up, activity-level breakdown by Config / Customisation / Data Migration + UT
Estimate Type (H / D) | D
→ Routing | ✔ You are in the right workbook — proceed with Detailed Estimation below
PROJECT METADATA
Client / Engagement | <<Enter Name>>
Oracle Modules in Scope | <<e.g. HCM, ERP, SCM, EPM>>
No. of Legal Entities | 3
Industry Vertical | <<e.g. Manufacturing>>
Estimation Basis | Bottom-Up Detailed (Activity Level)
Prepared By | <<Name>>
Date | <<DD-MMM-YYYY>>
Version | v1.0
WORKBOOK TAB GUIDE
Cover | This sheet — project metadata + estimate type selector | Input
Assumptions | Global levers: rates, working days, contingency, UT ratios | Input
Config Estimator | Bottom-up config effort: task × complexity × volume per module | Input+Calc
Custom Estimator | CEMLI / extension effort: object × type × Dev + UT days | Input+Calc
Data Migration Est. | Migration object effort: extract + cleanse + load + UT | Input+Calc
SDLC Phase View | Cross-pillar effort rolled up by SDLC phase across all three streams | Output
Role & FTE Summary | Effort by role, FTE loading, peak headcount | Output
Cost Summary | Total cost = effort × blended rates + contingency | Output

## Assumptions
GLOBAL ASSUMPTIONS & RATE CARD
All amber cells are inputs. Change here; all estimator sheets auto-update.
A. WORKING CALENDAR & CONTINGENCY
Parameter | Value | Unit | Min | Max | Note
Working Hours per Day | 8 | hrs | 7 | 9 | Standard billing day
Working Days per Month | 20 | days | 18 | 22 | Adjust for regional holidays
Contingency % | 15 | % | 10 | 25 | PMI / Oracle programme standard
Management Reserve % | 5 | % | 3 | 10 | Programme buffer — advisory
Onshore % | 30 | % | 0 | 100 | Delivery model split
Offshore % | 70 | % | 0 | 100 | Should sum to 100 with Onshore
UT % of Dev Effort (Config) | 20 | % | 15 | 30 | Unit test as % of config build effort
UT % of Dev Effort (Custom) | 30 | % | 25 | 40 | Unit test as % of CEMLI dev effort
UT % of Dev Effort (DataMig) | 25 | % | 20 | 35 | Reconciliation/UT as % of migration effort
Peer Review % (Custom only) | 10 | % | 5 | 15 | Code review overhead on custom dev
B. RATE CARD — BLENDED DAILY RATES (USD)
Role / Band | Onshore $/day | Offshore $/day | Blended $/day | Level | Typical Engagement %
Programme Director | 2200 | 900 | 1290 | Partner/Director | 3%
Solution Architect | 1800 | 750 | 1065 | Senior Manager | 5%
Functional Lead (per module) | 1500 | 600 | 870 | Senior Manager | 12%
Technical / Integration Lead | 1600 | 650 | 935 | Senior Manager | 8%
Functional Consultant Sr. | 1200 | 480 | 696 | Manager | 20%
Functional Consultant Mid | 900 | 360 | 522 | Senior Associate | 18%
ABAP / OIC Developer Sr. | 1000 | 400 | 580 | Manager | 8%
ABAP / OIC Developer Mid | 800 | 320 | 464 | Senior Associate | 7%
Data Migration Specialist | 1100 | 440 | 638 | Manager | 7%
Change Mgmt / OCM Lead | 1300 | 520 | 754 | Manager | 5%
Testing Lead / QA | 1000 | 400 | 580 | Manager | 4%
Project Manager | 1400 | 560 | 812 | Manager | 3%
C. COMPLEXITY MULTIPLIERS (editable)
Level | Code | Multiplier | Config | Selection Criteria | Examples (Config ¦ Custom ¦ Data Migration)
Low | L | 0.7 | 0.7 | • OOB / standard Oracle functionality; minimal configuration beyond defaults • Single legal entity or business unit; no country-specific localisation • Processes closely match Oracle standard; no workarounds or process redesign • Standard approval workflow (1–2 levels); standard RBAC roles sufficient • Source data is clean, well-structured, available in compatible format • Integration is one-way batch/file-based (SFTP/FTP); no transformation logic | CONFIG: › Single-country absence plans & holiday calendars › Standard expense policy with OOB approval CUSTOM: › One-way batch SFTP integration (file-based) › Standard OTBI report using a single subject area DATA MIG: › Reference data (departments, grades, jobs) — clean single source › Supplier master from single ERP, no duplicates, standard fields
Medium | M | 1 | 1 | • Some configuration beyond OOB; guided by Oracle best practice • 2–5 legal entities or business units sharing common structures • Minor process deviations handled via Oracle flexfields or lookups • Standard multi-level approval workflow (2–3 levels); standard security model • Source data requires moderate cleansing; mostly 1-to-1 field mapping • Standard REST/SOAP API integration; moderate transformation logic | CONFIG: › Multi-entity GL with intercompany accounting (3 entities) › AP invoice approval with 3-level BPM workflow CUSTOM: › OIC REST API integration (inbound/outbound, moderate mapping) › OTBI report across 2 subject areas with calculated measures DATA MIG: › Employee master from a single HR system with standard fields › Open AP invoices from a structured ERP with known schema
High | H | 1.4 | 1.5 | • Significant complexity; multiple exceptions to OOB process • 6–15 legal entities, multi-country, or cross-pillar dependencies • Legislative or regulatory requirements driving non-standard configuration • Complex multi-level approval hierarchies; data security policy design • Source data is poor quality, fragmented across systems, or unstructured • Real-time or bidirectional integration; event-driven or orchestrated flows | CONFIG: › Multi-country payroll with country-specific tax localisations (3+ countries) › WMS warehouse layout with advanced picking, putaway & replenishment rules CUSTOM: › Bidirectional real-time OIC integration with complex transformation logic › Custom payroll Fast Formula with tax override and conditional logic DATA MIG: › Employee data from 3+ HR systems with conflicting schemas › Fixed assets with full depreciation history and NBV reconciliation
Very High | VH | 1.9 | 2 | • Heavily customised or non-standard process; Oracle OOB not fit for purpose • 15+ legal entities, global rollout, or highly regulated (BFSI, Pharma, Defence) • High CEMLI dependency; multiple custom extensions interacting with each other • Real-time multi-system orchestration with complex event handling and retry logic • Legacy data with no clear mapping, large volumes, or critical statutory reconciliation • Concurrent go-live across multiple countries or business units in a single cutover | CONFIG: › Global payroll across 10+ countries with unique legislation per country › Holding company consolidation with complex minority interest & FX elimination CUSTOM: › ODA chatbot with NLP + multi-system backend orchestration › Multi-system integration hub (ERP + HCM + CRM + 3PL + Banking) DATA MIG: › Legacy COBOL mainframe data with reverse-engineered schema › Multi-country payroll balances with local statutory year-end carryforward

## Config Estimator
CONFIGURATION EFFORT ESTIMATOR
Activity-level config effort with Dev Days + Unit Test Days split ¦ Amber = input ¦ Green = calculated
AMBER = Input |  | GREEN = Calculated |  | BLUE = Formula |  | CX: L=Low M=Med H=High VH=VHigh
Module / Pillar | Configuration Task / Activity | Complexity (L/M/H/VH) | Volume (Count) | Unit Dev Days (OOB) | Benchmark Source | Complexity Multiplier | Base Dev Days | Unit Test Days (UT%) | Total Config Effort (Days) | SDLC: Build % split | Primary Role
▼ COMPLEXITY GUIDE — Configuration activities (Column D)
Select the code that best describes the majority of the work in this row. When in doubt between two levels, always choose the higher one and document your rationale. Multipliers are applied automatically from the Assumptions tab.
Level (Code) |  |  | Selection Criteria | [7 empty] | Typical Example for this Sheet
Low (L) ×0.7× |  |  | • OOB / standard Oracle functionality; minimal configuration beyond defaults • Single legal entity or business unit; no country-specific localisation • Processes closely match Oracle standard; no workarounds or process redesign • Standard approval workflow (1–2 levels); standard RBAC roles sufficient • Source data is clean, well-structured, available in compatible format • Integration is one-way batch/file-based (SFTP/FTP); no transformation logic | [7 empty] | › Single-country absence plans & holiday calendars › Standard expense policy with OOB approval › Item category setup with standard attributes
Medium (M) ×1.0× |  |  | • Some configuration beyond OOB; guided by Oracle best practice • 2–5 legal entities or business units sharing common structures • Minor process deviations handled via Oracle flexfields or lookups • Standard multi-level approval workflow (2–3 levels); standard security model • Source data requires moderate cleansing; mostly 1-to-1 field mapping • Standard REST/SOAP API integration; moderate transformation logic | [7 empty] | › Multi-entity GL with intercompany accounting (3 entities) › AP invoice approval with 3-level BPM workflow › Payroll element setup for a single-country payroll
High (H) ×1.4× |  |  | • Significant complexity; multiple exceptions to OOB process • 6–15 legal entities, multi-country, or cross-pillar dependencies • Legislative or regulatory requirements driving non-standard configuration • Complex multi-level approval hierarchies; data security policy design • Source data is poor quality, fragmented across systems, or unstructured • Real-time or bidirectional integration; event-driven or orchestrated flows | [7 empty] | › Multi-country payroll with country-specific tax localisations (3+ countries) › WMS warehouse layout with advanced picking, putaway & replenishment rules › Security RBAC design with SoD conflict identification and remediation
Very High (VH) ×2.0× |  |  | • Heavily customised or non-standard process; Oracle OOB not fit for purpose • 15+ legal entities, global rollout, or highly regulated (BFSI, Pharma, Defence) • High CEMLI dependency; multiple custom extensions interacting with each other • Real-time multi-system orchestration with complex event handling and retry logic • Legacy data with no clear mapping, large volumes, or critical statutory reconciliation • Concurrent go-live across multiple countries or business units in a single cutover | [7 empty] | › Global payroll across 10+ countries with unique legislation per country › Holding company consolidation with complex minority interest & FX elimination › Manufacturing with multi-level BOM, shop floor control, and IoT sensor integration
HCM – Core HR | Enterprise Structures setup (BU, LE, Divisions) | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Lead
| Reference Data: Grades, Grade Ladders, Job Families | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Consultant
| Position Management configuration | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Consultant
| Assignment & Employment Model setup | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Lead
| Work Schedules & Holiday Calendars | L | 1 | 3 | Everest 2023 | 0.7 | 2.1 | 0.42 | 2.52 | 65% | Functional Consultant
| Absence Plans & Eligibility Rules | M | 1 | 6 | Forrester TEI | 1 | 6 | 1.2 | 7.2 | 65% | Functional Consultant
| Document Records & DFF setup | L | 1 | 3 | Everest 2023 | 0.7 | 2.1 | 0.42 | 2.52 | 65% | Functional Consultant
HCM – Payroll | Payroll Definitions & Pay Frequencies | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Lead
| Earnings & Deduction Elements setup | H | 1 | 10 | Everest 2023 | 1.4 | 14 | 2.8 | 16.8 | 65% | Functional Lead
| Fast Formula development (per formula group) | H | 5 | 4 | Everest 2023 | 1.4 | 28 | 5.6 | 33.6 | 65% | Technical Developer
| Payroll Costing configuration | H | 1 | 6 | Forrester TEI | 1.4 | 8.4 | 1.68 | 10.08 | 65% | Functional Lead
| Tax Localisation per country | H | 3 | 8 | Gartner 2022 | 1.4 | 33.6 | 6.72 | 40.32 | 65% | Functional Lead
HCM – Talent | Recruiting: Requisition & Offer configuration | M | 1 | 5 | Forrester TEI | 1 | 5 | 1 | 6 | 65% | Functional Consultant
| Performance Template & Rating Model setup | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Consultant
| Goal Management & Library configuration | L | 1 | 3 | Everest 2023 | 0.7 | 2.1 | 0.42 | 2.52 | 65% | Functional Consultant
HCM – Benefits | Benefit Plans, Options & Coverage configuration | M | 1 | 8 | Everest 2023 | 1 | 8 | 1.6 | 9.6 | 65% | Functional Consultant
| Eligibility Profiles setup | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Consultant
ERP – GL | Chart of Accounts design (segments & values) | H | 1 | 10 | Forrester TEI | 1.4 | 14 | 2.8 | 16.8 | 65% | Functional Lead
| Ledger & Accounting Calendar setup | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Lead
| Intercompany Accounting configuration | H | 3 | 6 | Forrester TEI | 1.4 | 25.2 | 5.04 | 30.24 | 65% | Functional Lead
| Period Close procedures & Subledger Accounting | M | 1 | 6 | Everest 2023 | 1 | 6 | 1.2 | 7.2 | 65% | Functional Lead
ERP – AP | Supplier Setup: Sites, Banks, Payment Terms | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Consultant
| Invoice Processing & Approval Workflow | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Consultant
| Payment Templates & Bank configuration | M | 1 | 5 | Everest 2023 | 1.4 | 7 | 1.4 | 8.4 | 65% | Functional Consultant
ERP – AR | Customer Setup & Credit Management | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Consultant
| Receipt Methods & Lockbox configuration | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Consultant
| Revenue Recognition rules setup | H | 1 | 7 | Forrester TEI | 1 | 7 | 1.4 | 8.4 | 65% | Functional Lead
ERP – FA | Asset Books, Categories & Depreciation Methods | M | 1 | 7 | Everest 2023 | 1 | 7 | 1.4 | 8.4 | 65% | Functional Consultant
| Lease Accounting (ASC842/IFRS16) | H | 1 | 8 | Gartner 2022 | 1.4 | 11.2 | 2.24 | 13.44 | 65% | Functional Lead
ERP – Cash | Bank Accounts & Reconciliation setup | M | 1 | 4 | Everest 2023 | 1 | 4 | 0.8 | 4.8 | 65% | Functional Consultant
ERP – Tax | Tax Regime, Rates & Rules configuration | H | 3 | 6 | Forrester TEI | 1.4 | 25.2 | 5.04 | 30.24 | 65% | Technical Lead
ERP – Expense | Expense Policies, Approval & Corporate Cards | L | 1 | 4 | Everest 2023 | 0.7 | 2.8 | 0.56 | 3.36 | 65% | Functional Consultant
ERP – Proc | Purchasing Config: Approval Hierarchies, Document styles | M | 1 | 6 | Everest 2023 | 1 | 6 | 1.2 | 7.2 | 65% | Functional Consultant
| Requisition & PO Workflow setup | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Consultant
| Supplier Portal configuration | M | 1 | 5 | Forrester TEI | 1 | 5 | 1 | 6 | 65% | Functional Consultant
SCM – INV | Inventory Organisations & Sub-Inventories | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Lead
| Item Master & Item Attributes setup | M | 1 | 6 | Everest 2023 | 1 | 6 | 1.2 | 7.2 | 65% | Functional Consultant
| Lot, Serial, Revision control configuration | H | 1 | 5 | Everest 2023 | 1.4 | 7 | 1.4 | 8.4 | 65% | Functional Consultant
SCM – OMS | Order Types, Lines & Fulfilment setup | H | 1 | 8 | Forrester TEI | 1.4 | 11.2 | 2.24 | 13.44 | 65% | Functional Lead
| Pricing Strategy & Price Lists | M | 1 | 6 | Everest 2023 | 1 | 6 | 1.2 | 7.2 | 65% | Functional Lead
SCM – MFG | Bills of Material & Routing setup | H | 1 | 8 | Everest 2023 | 1.4 | 11.2 | 2.24 | 13.44 | 65% | Functional Lead
| Work Definitions & Resource setup | H | 1 | 7 | Everest 2023 | 1.4 | 9.8 | 1.96 | 11.76 | 65% | Functional Lead
SCM – WMS | Warehouse Layout & Strategies | H | 1 | 10 | Gartner 2022 | 1.4 | 14 | 2.8 | 16.8 | 65% | Functional Lead
| Picking & Putaway Rules configuration | H | 1 | 8 | Gartner 2022 | 1.4 | 11.2 | 2.24 | 13.44 | 65% | Functional Lead
SCM – QA | Inspection Plans & Sampling Rules | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Functional Consultant
EPM – EPBCS | Planning Application & Dimensions setup | H | 1 | 12 | Forrester TEI | 1.4 | 16.8 | 3.36 | 20.16 | 65% | Functional Lead
| Budget Forms, Approval Workflow | H | 1 | 8 | Gartner 2022 | 1.4 | 11.2 | 2.24 | 13.44 | 65% | Functional Lead
EPM – FCCS | Consolidation App & Intercompany Elimination rules | H | 1 | 12 | Gartner 2022 | 1.4 | 16.8 | 3.36 | 20.16 | 65% | Functional Lead
EPM – ARCS | [6 empty] | 0 | 0 | 0 | 65% | Functional Consultant
Security | [6 empty] | 0 | 0 | 0 | 65% | Functional Lead
| Data Security Policies per module | H | 1 | 8 | Gartner 2022 | 1.4 | 11.2 | 2.24 | 13.44 | 65% | Technical Lead
| SoD Conflict Rules & Remediation | H | 1 | 10 | Forrester TEI | 1.4 | 14 | 2.8 | 16.8 | 65% | Functional Lead
| SSO / IDCS / SAML configuration | M | 1 | 6 | Everest 2023 | 1 | 6 | 1.2 | 7.2 | 65% | Technical Lead
Infrastructure | OCI Environment provisioning (DEV/TEST/PROD) | M | 1 | 8 | Everest 2023 | 1 | 8 | 1.6 | 9.6 | 65% | Infra Engineer
| Network, VPN & Security Zones setup | M | 1 | 5 | Everest 2023 | 1 | 5 | 1 | 6 | 65% | Infra Engineer
| Scheduled Jobs & ESS configuration | L | 1 | 3 | Everest 2023 | 0.7 | 2.1 | 0.42 | 2.52 | 65% | Technical Lead
CONFIGURATION TOTALS | [6 empty] | 466.2 | 93.24 | 559.44
TOTAL CONFIG EFFORT WITH CONTINGENCY (+15%) | [8 empty] | 643.356

## Custom Estimator
CUSTOMISATION (CEMLI) EFFORT ESTIMATOR
Bottom-up CEMLI effort: Dev Days + Unit Test + Peer Review split ¦ Amber = input ¦ Green = calculated
UT Days = Dev Days × UT% (Assumptions C8) ¦ Peer Review = Dev Days × Review% (Assumptions C10) ¦ Total = Dev + UT + Review ¦ Complexity multiplier from Assumptions Section C (col E = Custom)
Module | Extension Name / Description | Extension Type | CX (L/M/H/VH) | Qty | Unit Dev Days | CX Multiplier | Base Dev Days | UT Days (UT%) | Peer Rev Days | Total Effort(Days) | Benchmark | Primary Role
▼ COMPLEXITY GUIDE — CEMLI / Extension activities (Column E)
Select the code that best describes the majority of the work in this row. When in doubt between two levels, always choose the higher one and document your rationale. Multipliers are applied automatically from the Assumptions tab.
Level (Code) |  |  | Selection Criteria | [8 empty] | Typical Example for this Sheet
Low (L) ×0.8× |  |  | • OOB / standard Oracle functionality; minimal configuration beyond defaults • Single legal entity or business unit; no country-specific localisation • Processes closely match Oracle standard; no workarounds or process redesign • Standard approval workflow (1–2 levels); standard RBAC roles sufficient • Source data is clean, well-structured, available in compatible format • Integration is one-way batch/file-based (SFTP/FTP); no transformation logic | [8 empty] | › One-way batch SFTP integration (file-based) › Standard OTBI report using a single subject area › Simple page personalisation (hide/show fields)
Medium (M) ×1.0× |  |  | • Some configuration beyond OOB; guided by Oracle best practice • 2–5 legal entities or business units sharing common structures • Minor process deviations handled via Oracle flexfields or lookups • Standard multi-level approval workflow (2–3 levels); standard security model • Source data requires moderate cleansing; mostly 1-to-1 field mapping • Standard REST/SOAP API integration; moderate transformation logic | [8 empty] | › OIC REST API integration (inbound/outbound, moderate mapping) › OTBI report across 2 subject areas with calculated measures › BPM workflow extension with conditional routing
High (H) ×1.5× |  |  | • Significant complexity; multiple exceptions to OOB process • 6–15 legal entities, multi-country, or cross-pillar dependencies • Legislative or regulatory requirements driving non-standard configuration • Complex multi-level approval hierarchies; data security policy design • Source data is poor quality, fragmented across systems, or unstructured • Real-time or bidirectional integration; event-driven or orchestrated flows | [8 empty] | › Bidirectional real-time OIC integration with complex transformation logic › Custom payroll Fast Formula with tax override and conditional logic › OAC dashboard with cross-pillar KPIs and multi-source calculated metrics
Very High (VH) ×1.9× |  |  | • Heavily customised or non-standard process; Oracle OOB not fit for purpose • 15+ legal entities, global rollout, or highly regulated (BFSI, Pharma, Defence) • High CEMLI dependency; multiple custom extensions interacting with each other • Real-time multi-system orchestration with complex event handling and retry logic • Legacy data with no clear mapping, large volumes, or critical statutory reconciliation • Concurrent go-live across multiple countries or business units in a single cutover | [8 empty] | › ODA chatbot with NLP + multi-system backend orchestration › Multi-system integration hub (ERP + HCM + CRM + 3PL + Banking) › Custom statutory report replacing a government submission format
HCM – Payroll | Custom Fast Formula — Tax Override | Formula | H | 3 | 5 | 1.5 | 22.5 | 6.75 | 2.25 | 31.5 | Everest 2023 | Technical Developer
| Custom Payslip Layout (BI Publisher) | BI Publisher | M | 2 | 6 | 1 | 12 | 3.6 | 1.2 | 16.8 | Everest 2023 | Technical Developer
HCM – Core HR | Person Address Validation Extension | Page Ext (VB) | M | 2 | 4 | 1 | 8 | 2.4 | 0.8 | 11.2 | Everest 2023 | Technical Developer
HCM – Talent | Custom Offer Letter Template | BI Publisher | L | 2 | 4 | 0.7 | 5.6 | 1.68 | 0.56 | 7.84 | Everest 2023 | Technical Developer
ERP – GL | Journal Import Custom Validation Rule | Business Rule | H | 2 | 5 | 1.5 | 15 | 4.5 | 1.5 | 21 | Forrester TEI | Technical Developer
ERP – AP | Custom Invoice Approval Workflow Ext | Workflow Ext | H | 1 | 8 | 1.5 | 12 | 3.6 | 1.2 | 16.8 | Gartner 2022 | Technical Lead
| Custom Payment File Format (ISO20022) | BI Publisher | H | 2 | 8 | 1.5 | 24 | 7.2 | 2.4 | 33.6 | Forrester TEI | Technical Lead
ERP – AR | Custom AutoInvoice Interface Validation | Business Rule | M | 1 | 5 | 1 | 5 | 1.5 | 0.5 | 7 | Everest 2023 | Technical Developer
ERP – FA | Custom Asset Depreciation Report | OTBI/BIP | M | 1 | 6 | 1 | 6 | 1.8 | 0.6 | 8.4 | Everest 2023 | Technical Developer
ERP – Tax | Tax Determination Custom Rule | Business Rule | H | 3 | 6 | 1.5 | 27 | 8.1 | 2.7 | 37.8 | Forrester TEI | Technical Lead
ERP – Proc | Custom PO Approval Notification | BPM Workflow | M | 1 | 6 | 1 | 6 | 1.8 | 0.6 | 8.4 | Everest 2023 | Technical Developer
| Supplier Portal Custom Page Extension | Page Ext (VB) | M | 1 | 5 | 1 | 5 | 1.5 | 0.5 | 7 | Everest 2023 | Technical Developer
SCM – OMS | Custom Pricing Algorithm Extension | Business Rule | H | 1 | 10 | 1.5 | 15 | 4.5 | 1.5 | 21 | Gartner 2022 | Technical Lead
| Custom Order Fulfilment Orchestration | OIC Flow | H | 2 | 10 | 1.5 | 30 | 9 | 3 | 42 | Forrester TEI | Technical Lead
SCM – MFG | Custom Production Dispatch Report | OTBI/BIP | M | 2 | 5 | 1 | 10 | 3 | 1 | 14 | Everest 2023 | Technical Developer
SCM – WMS | Custom Barcode Label Layout | BI Publisher | L | 2 | 3 | 0.7 | 4.2 | 1.26 | 0.42 | 5.88 | Everest 2023 | Technical Developer
Integration | OIC Flow — HCM to Payroll Provider | OIC (Complex) | H | 1 | 14 | 1.5 | 21 | 6.3 | 2.1 | 29.4 | Everest 2023 | Technical Lead
| OIC Flow — ERP to Banking (ISO20022) | OIC (Complex) | H | 1 | 14 | 1.5 | 21 | 6.3 | 2.1 | 29.4 | Forrester TEI | Technical Lead
| OIC Flow — SCM to 3PL Warehouse | OIC (Complex) | H | 2 | 14 | 1.5 | 42 | 12.6 | 4.2 | 58.8 | Forrester TEI | Technical Lead
| REST API — CRM to ERP Order | OIC (Simple) | M | 3 | 6 | 1 | 18 | 5.4 | 1.8 | 25.2 | Everest 2023 | Technical Lead
| REST API — ERP to Tax Engine (Avalara) | OIC (Simple) | M | 1 | 8 | 1 | 8 | 2.4 | 0.8 | 11.2 | Everest 2023 | Technical Lead
| File-Based SFTP Integration (batch) | OIC (Simple) | L | 5 | 4 | 0.7 | 14 | 4.2 | 1.4 | 19.6 | Everest 2023 | Technical Developer
| Event-Driven ODA Chatbot Integration | OIC (Complex) | H | 1 | 16 | 1.5 | 24 | 7.2 | 2.4 | 33.6 | Gartner 2022 | Technical Lead
Reporting | OTBI Analysis — GL Trial Balance | OTBI | M | 2 | 3 | 1 | 6 | 1.8 | 0.6 | 8.4 | Everest 2023 | Technical Developer
[7 empty] | 0 | 0 | 0 | 0 | Everest 2023 | Technical Developer
[7 empty] | 0 | 0 | 0 | 0 | Everest 2023 | Technical Developer
| BIP Report — PO Output Format | BI Publisher | M | 1 | 5 | 1.5 | 7.5 | 2.25 | 0.75 | 10.5 | Everest 2023 | Technical Developer
| OAC Dashboard — Finance KPIs | OAC | H | 2 | 10 | 1.5 | 30 | 9 | 3 | 42 | Gartner 2022 | Technical Lead
| OAC Dashboard — Supply Chain Ops | OAC | H | 1 | 10 | 1.5 | 15 | 4.5 | 1.5 | 21 | Gartner 2022 | Technical Lead
| BIP Report — Vendor Payment Remittance | BI Publisher | M | 1 | 5 | 1 | 5 | 1.5 | 0.5 | 7 | Everest 2023 | Technical Developer
EPM | Smart View Custom Template | SmartView | M | 2 | 5 | 1 | 10 | 3 | 1 | 14 | Gartner 2022 | Technical Developer
| Groovy Calculation Script (EPBCS) | Calc Script | H | 3 | 8 | 1.5 | 36 | 10.8 | 3.6 | 50.4 | Gartner 2022 | Technical Lead
CUSTOMISATION TOTALS | [6 empty] | 464.8 | 139.44 | 46.48 | 650.72
TOTAL CUSTOM EFFORT WITH CONTINGENCY | [9 empty] | 748.328

## Data Migration Est.
DATA MIGRATION EFFORT ESTIMATOR
Bottom-up per migration object: Extract + Cleanse + Transform + Load + Recon/UT ¦ Amber = input
UT / Reconciliation Days = (Extract+Cleanse+Transform+Load) × UT% from Assumptions C9 ¦ All effort is per migration object (one FBDI/HDL template). Volume = number of trial load cycles (default 3).
Module | Migration Object | Tool (FBDI/HDL) | CX (L/M/H) | Trial Loads (Vol) | Extract Days | Cleanse Days | Transform Days | Load Days | Recon/UT Days | Sub-Total Dev Days | Total incl UT (Days) | Benchmark / Role
▼ COMPLEXITY GUIDE — Data Migration objects (Column E)
Select the code that best describes the majority of the work in this row. When in doubt between two levels, always choose the higher one and document your rationale. Multipliers are applied automatically from the Assumptions tab.
Level (Code) |  |  | Selection Criteria | [8 empty] | Typical Example for this Sheet
Low (L) ×0.7× |  |  | • OOB / standard Oracle functionality; minimal configuration beyond defaults • Single legal entity or business unit; no country-specific localisation • Processes closely match Oracle standard; no workarounds or process redesign • Standard approval workflow (1–2 levels); standard RBAC roles sufficient • Source data is clean, well-structured, available in compatible format • Integration is one-way batch/file-based (SFTP/FTP); no transformation logic | [8 empty] | › Reference data (departments, grades, jobs) — clean single source › Supplier master from single ERP, no duplicates, standard fields › GL chart of accounts with clear legacy mapping
Medium (M) ×1.0× |  |  | • Some configuration beyond OOB; guided by Oracle best practice • 2–5 legal entities or business units sharing common structures • Minor process deviations handled via Oracle flexfields or lookups • Standard multi-level approval workflow (2–3 levels); standard security model • Source data requires moderate cleansing; mostly 1-to-1 field mapping • Standard REST/SOAP API integration; moderate transformation logic | [8 empty] | › Employee master from a single HR system with standard fields › Open AP invoices from a structured ERP with known schema › Item master with 50–70% direct attribute mapping
High (H) ×1.4× |  |  | • Significant complexity; multiple exceptions to OOB process • 6–15 legal entities, multi-country, or cross-pillar dependencies • Legislative or regulatory requirements driving non-standard configuration • Complex multi-level approval hierarchies; data security policy design • Source data is poor quality, fragmented across systems, or unstructured • Real-time or bidirectional integration; event-driven or orchestrated flows | [8 empty] | › Employee data from 3+ HR systems with conflicting schemas › Fixed assets with full depreciation history and NBV reconciliation › BOM/routing from legacy MRP with non-standard structure and UoM
Very High (VH) ×2.0× |  |  | • Heavily customised or non-standard process; Oracle OOB not fit for purpose • 15+ legal entities, global rollout, or highly regulated (BFSI, Pharma, Defence) • High CEMLI dependency; multiple custom extensions interacting with each other • Real-time multi-system orchestration with complex event handling and retry logic • Legacy data with no clear mapping, large volumes, or critical statutory reconciliation • Concurrent go-live across multiple countries or business units in a single cutover | [8 empty] | › Legacy COBOL mainframe data with reverse-engineered schema › Multi-country payroll balances with local statutory year-end carryforward › Inventory from 5+ legacy WMS systems with conflicting UoM, codes and structures
HCM | Employees (Person, Assignment, Contract) | HDL | H | 1 | 8 | 12 | 6 | 4 | 4 | 42 | 58.1 | Everest 2023 ¦ DM Specialist
| Organisation Hierarchy & Departments | HDL | M | 1 | 3 | 5 | 3 | 2 | 2 | 13 | 18.25 | Everest 2023 ¦ DM Specialist
| Jobs, Positions & Grades | HDL | M | 1 | 2 | 3 | 2 | 2 | 1 | 9 | 12.25 | Everest 2023 ¦ Functional Consultant
| Work Relationships & Contracts | HDL | H | 1 | 4 | 6 | 4 | 3 | 3 | 23.8 | 33.95 | Everest 2023 ¦ DM Specialist
| Compensation & Salary History | HCM Spreadsheet | H | 1 | 4 | 8 | 4 | 3 | 3 | 26.6 | 37.45 | Forrester TEI ¦ DM Specialist
| Absence Balances & Accruals | HCM Spreadsheet | M | 1 | 2 | 4 | 3 | 2 | 2 | 11 | 15.75 | Everest 2023 ¦ DM Specialist
ERP | Chart of Accounts & Account Values | FBDI | H | 1 | 3 | 5 | 3 | 2 | 3 | 18.2 | 26.95 | Everest 2023 ¦ DM Specialist
| Open AP Invoices | FBDI | H | 1 | 3 | 6 | 4 | 3 | 4 | 22.4 | 33.6 | Forrester TEI ¦ DM Specialist
| Open AR Transactions | FBDI | H | 1 | 3 | 6 | 4 | 3 | 4 | 22.4 | 33.6 | Forrester TEI ¦ DM Specialist
| Fixed Assets — Asset Details & NBV | FBDI | H | 1 | 4 | 8 | 5 | 4 | 5 | 29.4 | 43.75 | Gartner 2022 ¦ DM Specialist
| GL Open Balances (per period) | FBDI | M | 1 | 3 | 4 | 3 | 2 | 3 | 12 | 18 | Everest 2023 ¦ DM Specialist
| Supplier Master & Supplier Sites | FBDI | M | 1 | 3 | 5 | 3 | 2 | 2 | 13 | 18.25 | Everest 2023 ¦ Functional Consultant
| Customer Master & Customer Sites | FBDI | M | 1 | 3 | 5 | 3 | 2 | 2 | 13 | 18.25 | Everest 2023 ¦ Functional Consultant
[10 empty] | 0 | 0 | Everest 2023 ¦ DM Specialist
SCM | [9 empty] | 0 | 0 | Everest 2023 ¦ DM Specialist
| Bill of Materials (BOM) | FBDI | H | 1 | 4 | 8 | 5 | 4 | 4 | 29.4 | 42.35 | Gartner 2022 ¦ DM Specialist
| On-Hand Inventory Balances | FBDI | M | 1 | 3 | 5 | 3 | 3 | 3 | 14 | 20.5 | Everest 2023 ¦ DM Specialist
| Open Sales Orders | FBDI | H | 1 | 4 | 6 | 4 | 3 | 3 | 23.8 | 33.95 | Everest 2023 ¦ DM Specialist
| Routings & Resources | FBDI | H | 1 | 3 | 6 | 4 | 3 | 3 | 22.4 | 32.2 | Everest 2023 ¦ DM Specialist
EPM | Historical Financial Data (FCCS) | Data Management | H | 1 | 5 | 10 | 6 | 4 | 5 | 35 | 50.75 | Gartner 2022 ¦ DM Specialist
| Budget / Plan Data (EPBCS) | Data Management | M | 1 | 3 | 5 | 4 | 3 | 3 | 15 | 21.75 | Gartner 2022 ¦ DM Specialist
DATA MIGRATION TOTALS | [9 empty] | 395.4 | 569.65
TOTAL DATA MIGRATION WITH CONTINGENCY | [10 empty] | 655.0975

## SDLC Phase View
SDLC PHASE EFFORT VIEW
Cross-stream effort rolled up by SDLC phase ¦ References Config, Custom & Data Migration sheets
A. SOURCE STREAM TOTALS (with Contingency)
Stream | Total Effort (Days) | Dev Days | UT / Recon Days | Source Sheet
Configuration | 643.356 | 0 | 0 | Config Estimator — Col K
Customisation (CEMLI) | 748.328 | 0 | 0 | Custom Estimator — Col L
Data Migration | 655.0975 | 0 | 0 | Data Migration Est. — Col M
GRAND TOTAL (all streams) | 2046.7815 | 0 | 0
B. EFFORT BY SDLC PHASE — ALL STREAMS
SDLC Phase | Config Effort | Custom Effort | Data Mig Effort | Total Phase Effort | % of Grand Total | Elapsed Weeks (est) | Phase FTE (avg)
Ph0: Inception/Mobilise | 19.3007 | 14.9666 | 32.7549 | 67.0221 | 3.275% | 3.87 | 0
Ph1: Discover & Assess | 77.2027 | 37.4164 | 98.2646 | 212.8837 | 10.4% | 9.288 | 0
Ph2: Design/Blueprint | 115.8041 | 112.2492 | 65.5097 | 293.563 | 14.34% | 13.932 | 0
Ph3: Build / Configure | 257.3424 | 336.7476 | 163.7744 | 757.8644 | 37.03% | 21.672 | 0
Ph4: Integration & SIT | 64.3356 | 134.699 | 32.7549 | 231.7895 | 11.32% | 9.288 | 0
Ph5: UAT | 51.4685 | 74.8328 | 32.7549 | 159.0562 | 7.771% | 6.192 | 0
Ph6: Data Migration | 0 | 0 | 163.7744 | 163.7744 | 8.002% | 6.192 | 0
Ph7: Training & OCM | 25.7342 | 14.9666 | 19.6529 | 60.3537 | 2.949% | 3.87 | 0
Ph8: Go-Live & Cutover | 19.3007 | 14.9666 | 32.7549 | 67.0221 | 3.275% | 1.548 | 0
Ph9: Post Go-Live/Hypercare | 12.8671 | 7.4833 | 13.102 | 33.4524 | 1.634% | 1.548 | 0
TOTAL | 643.356 | 748.328 | 655.0975 | 2046.7815
C. PHASE DEFINITIONS & KEY DELIVERABLES
Phase | Oracle OUM Ref | % Config | % Custom | % DataMig | Key Activities / Deliverables
Ph0: Inception/Mobilise | Phase 0 | 3% | 2% | 5% | Infra, kick-off, governance, templates
Ph1: Discover & Assess | OUM: Inception | 12% | 5% | 15% | CRP1, current state, gap analysis
Ph2: Design/Blueprint | OUM: Elaboration | 18% | 15% | 10% | Future state, CRP2, solution design
Ph3: Build / Configure | OUM: Construction | 40% | 45% | 25% | Config, Dev, Unit Test — heaviest phase
Ph4: Integration & SIT | OUM: Construction | 10% | 18% | 5% | OIC flows, SIT, defect cycles
Ph5: UAT | OUM: Transition | 8% | 10% | 5% | Business-led UAT, defect fix, sign-off
Ph6: Data Migration | OUM: Transition | 0% | 0% | 25% | Trial loads, reconciliation, cutover data
Ph7: Training & OCM | OUM: Transition | 4% | 2% | 3% | Training delivery, change comms
Ph8: Go-Live & Cutover | OUM: Production | 3% | 2% | 5% | Cutover weekend, parallel run
Ph9: Post Go-Live/Hypercare | OUM: Production | 2% | 1% | 2% | Stabilisation, L1/L2 hypercare

## Role & FTE Summary
ROLE EFFORT & FTE SUMMARY
Effort by role across all three streams ¦ FTE = Effort ÷ (Project Months × Working Days/Month)
A. EFFORT BY ROLE — CROSS-STREAM SUMMARY
Role / Band | Config Days | Custom Days | Data Mig Days | Total Days | % of Total | Avg FTE (18 mths) | Peak FTE
Programme Director | 12.8671 | 7.4833 | 6.551 | 26.9014 | 1.302% | 0 | 0
Solution Architect | 32.1678 | 44.8997 | 19.6529 | 96.7204 | 4.681% | 0 | 0
Functional Lead (HCM) | 77.2027 | 7.4833 | 26.2039 | 110.8899 | 5.366% | 0 | 0
Functional Lead (Finance) | 70.7692 | 7.4833 | 39.3058 | 117.5583 | 5.689% | 0 | 0
Functional Lead (SCM) | 64.3356 | 7.4833 | 39.3058 | 111.1247 | 5.378% | 0 | 0
Technical/Integration Lead | 19.3007 | 164.6322 | 32.7549 | 216.6877 | 10.49% | 0 | 0
Functional Consultant Sr. | 128.6712 | 14.9666 | 52.4078 | 196.0456 | 9.487% | 0 | 0
Functional Consultant Mid | 115.8041 | 14.9666 | 39.3058 | 170.0765 | 8.23% | 0 | 0
ABAP/OIC Developer Sr. | 12.8671 | 187.082 | 26.2039 | 226.153 | 10.94% | 0 | 0
ABAP/OIC Developer Mid | 6.4336 | 149.6656 | 19.6529 | 175.7521 | 8.505% | 0 | 0
Data Migration Specialist | 12.8671 | 14.9666 | 294.7939 | 322.6276 | 15.61% | 0 | 0
Change Mgmt / OCM Lead | 19.3007 | 7.4833 | 13.102 | 39.8859 | 1.93% | 0 | 0
Testing Lead / QA | 25.7342 | 59.8662 | 32.7549 | 118.3554 | 5.728% | 0 | 0
Project Manager | 25.7342 | 22.4498 | 19.6529 | 67.837 | 3.283% | 0 | 0
Infrastructure Engineer | 19.3007 | 37.4164 | 13.102 | 69.819 | 3.379% | 0 | 0
TOTAL | 643.356 | 748.328 | 674.7504 | 2066.4344 | 100.0% | 0
B. FTE RAMP — INDICATIVE MONTHLY HEADCOUNT
Role | M1 | M2 | M3 | M4 | M5 | M6 | M7
Programme Director | 1 | 1 | 1 | 1 | 1 | 1 | 1
Solution Architect | 1 | 2 | 2 | 2 | 2 | 1 | 1
Functional Leads (×3) |  | 1 | 2 | 3 | 3 | 3 | 2
Functional Consultants (×3) |  | 1 | 2 | 3 | 4 | 4 | 3
Tech/Integration Lead |  | 1 | 1 | 2 | 2 | 2 | 2
Developers (×2) |  |  | 1 | 2 | 2 | 2 | 2
Data Migration Specialist |  | 1 | 1 | 1 | 1 | 2 | 2
Testing Lead |  |  |  | 1 | 1 | 1 | 2
Project Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Cost Summary
COST SUMMARY — ORACLE FUSION DETAILED ESTIMATE
Effort × Blended Rates ¦ Three streams ¦ Contingency from Assumptions C3
A. COST BY STREAM
Stream | Effort (Days) | Blended Rate ($/day) | Base Cost ($) | Contingency ($) | Total Cost ($) | % of Total
Configuration | 643.356 | 696 | 447775.776 | 0 | 447775.776
Customisation (CEMLI) | 748.328 | 638 | 477433.264 | 0 | 477433.264
Data Migration | 655.0975 | 638 | 417952.205 | 0 | 417952.205
GRAND TOTAL | 2046.7815 |  | 1343161.245 | 0 | 1343161.245
B. INDICATIVE COST BY SDLC PHASE
SDLC Phase | % of Effort | Phase Cost ($) | Config Cost | Custom Cost | DataMig Cost | Phase FTE
Ph0: Inception/Mobilise | 5% | 67158.0623 | 13433.2733 | 9548.6653 | 20897.6103 | 0
Ph1: Discover & Assess | 12% | 161179.3494 | 53733.0931 | 23871.6632 | 62692.8308 | 0
Ph2: Design/Blueprint | 18% | 241769.0241 | 80599.6397 | 71614.9896 | 41795.2205 | 0
Ph3: Build / Configure | 28% | 376085.1486 | 179110.3104 | 214844.9688 | 104488.0513 | 0
Ph4: Integration & SIT | 12% | 161179.3494 | 44777.5776 | 85937.9875 | 20897.6103 | 0
Ph5: UAT | 8% | 107452.8996 | 35822.0621 | 47743.3264 | 20897.6103 | 0
Ph6: Data Migration | 8% | 107452.8996 | 0 | 0 | 104488.0513 | 0
Ph7: Training & OCM | 5% | 67158.0623 | 17911.031 | 9548.6653 | 12538.5662 | 0
Ph8: Go-Live & Cutover | 2% | 26863.2249 | 13433.2733 | 9548.6653 | 20897.6103 | 0
Ph9: Post Go-Live/Hypercare | 2% | 26863.2249 | 8955.5155 | 4774.3326 | 8359.0441 | 0
C. NOTE: Blended rates in column D above are editable — adjust per engagement
Default blended rates: Config stream uses Functional Consultant blended rate (Assumptions row 21). Customisation uses Developer blended rate. Data Migration uses DM Specialist rate. Override column D to use a project-specific blended rate per stream. For a role-by-role cost view, reference the Role & FTE Summary tab.